## CRG-FH-ITP-0017
|  |  | Inspection and Test Plan - Underground Stormwater Drainage | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-002
[11 empty] | Revision : 00 | 2025-05-05
Client: | Department of Transport & Planning |  | Construction Process: | Underground Stormwater Drainage |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melton Hwy/Leakes Road Upgrade |  |  |  |  | Name: | Mustafa Kamel | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT31608 |  | Specifications: | VicRoads Specifications Sec. 610 (Feb-20), 619 (Dec-17), 701 (Apr-19), 705 (May-20) |  | Position: | Senior Project Engineer |  | Delivery Manager |  |  | Delivery Manager
|  |  | Structure / Component: | Drainage Pipes, Culverts, Pits and Headwalls
|  |  | Location: |  |  | Date : | 2025-05-05 | Date : | 2025-05-05 |  | Date : | 2025-05-05
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman GPP Coordinator | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Stormwater Products and Materials
1.1 | Drainage Pipes |  | Prior to Commencing Work | Drainage pipes and culverts supplied in accordance with 701 and AS/NZS 4058. Documentation as per 701.05 is available in Teambinder Material Approval form | 701.04, 701.05 | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.2 | Drainage Pits |  | Prior to Commencing Work | - Drainage Pits are supplied in accordance with 705.07. - Pits deeper than 1m to be fitted with step irons as shown on the drawings. Step irons to be compliant with AS4680. - Suppliers documentation has been submitted via Teambinder Material Approval form | 705.07 | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.3 | Drainage Bedding Material |  | Prior to Commencing Work | Bedding Materials comply with Table 701.081 and 701.082. Material Approved via Teambinder Material Approval Form. | Table 701.081, Table 701.082 | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.4 | Drainage Backfill Material |  | Prior to Commencing Work | Select and Ordinary Backfill Materials comply with tables 701.081 and 701.082 Material Approved via Teambinder Material Approval form. | Table 701.081, Table 701.082 | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.5 | Bedding & Backfill Material Testing |  | 1 per 1,000 tonnes or part thereof | Bedding and backfill material tested at to ensure materials comply with the following: | Table 701.091, Table 701.092, Cl. 701.29, Table 701.291 | Grading and Plasticity Index | Test Records | TP | Engineer | N/A |  | N/A
1.6 | Material Inspection |  | Each Delivery | Material inspection to be completed for all precast pits, pipes and culverts. | Order Acceptance Form | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
2 | Preliminary Works
2.1 | Work pack briefing |  | Prior to Commencing Work | All personnel on site have been briefed on the relevant work park to scope of works. | WP | Document Review | Work pack signed. | HP* | Engineer / Foreman | N/A |  | N/A
2.2 | Check that current revision drawings are being used |  | Prior to Commencing Work | Issued For Construction (IFC) and latest available design revision in use. | IFC Project Drawings/ Drawing Register | Document review | Latest revision IFC drawings | HP* | Engineer / Foreman | N/A |  | N/A
2.3 | Ground Penetration Permit (GPP) issued |  | Prior to Commencing Work | Current GPP signed and specific to the area where works will be executed. Including walk through of the work area with the site team and GPP Coordinator prior to works. | Excavation Permit | Document review & Site inspection | Excavation Permit # | HP* | Engineer / GPP Coordinator | N/A |  | N/A
2.4 | Usage of HDPE Pipes |  | Pre Process Approval | HDPE (Stormpro/Blackmax) pipes to be used only under non-paved areas inlin with the latest design. | VicRoads Spec. Cl.619 Cl. 701.04 Cl. 701.05(a) AS4058 AS4680 | Teambinder Material Approval | Manufacturer cetificate or accreditation | IP | Engineer | N/A |  | N/A
2.5 | Backfilling with cement stabilised sand (If required) |  | Each drainage line | Subject to superintendent approval, underground stormwater drains may be backfilled to half the pipe diameter or box culvert height with 3% stabilised sand. Mixture to have a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water. | VicRoads Spec. Cl. 701.19(c) | Site Inspection | Superintendents Correspondence ITP signed | AP | Engineer / Superintendent |  |  | N/A
3 | Installation of Drainage
3.1 | Confirm position of culverts |  | Prior to commencing drainage line | Prior to commencement of excavation for the culverts and stormwater drainage, confirm the position with the Superintendent. | VicRoads Spec. Cl. 701.10 IFC Drawing | Site Inspection | Design and survey setout postion confirmed with Superintendent. | HP* | Engineer / Foreman |  |  | N/A
3.2 | Excavation |  | Each trench | Ensure trench is excavated to prepare culvert foundation and specified depth of bedding. Box culverts: - distance between culvert wall and trench wall is between 0.5 - 1.0 x the overall height of the culvert. Pipe culverts: - the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is greater than >300mm, less than <600mmm. Pits: - Clearance from external faces of the pit to each face of the excavation to be not less than 400mm | VicRoads Spec. Cl. 701.15 Table 701.151 Cl. 705.05(b) | Site Inspection Measurements of trench | ITP signed | IP | Engineer | N/A |  | N/A
3.3 | Bedding |  | Each trench | Bedding material shall be provided and placed for the full width of the trench. The compacted thickness of bedding material following any shaping necessary shall be: - minimum 100mm for pipes of D< 1500mm - minimum 200mm for pipes with D ≥ 1500 mm 'D' is the nominal pipe diameter or culvert width. Bedding and backfill materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Once culvert sections are in position, an additional layer of bedding material is placed to a height equal to 30% of the nominal pipe diameter or culvert height. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. | VicRoads Spec. Cl. 701.16 Cl. 701.20(a) | Site Inspection | Test Report | IP | Engineer | N/A |  | N/A
3.4 | Laying - Circular Pipe |  | Each culvert | Rebate and socket ends of pipe sections are positioned facing upstream and are to be fully entered. (Laying from downstream) The lower portion of the pipe shall be in contact with the bedding for the full length of each section. The compacted bedding shall be shaped to accommodate the joint collar and ensure that the pipe is supported along its full length. Where applicable, the top of the pipe as marked shall be within five degrees of the vertical axis of the culvert. Spacing of multiple rows of culverts to reflect Table 701.171. | VicRoads Spec. Cl. 701.17(b) | Site Inspection | ITP signed | IP | Engineer | N/A |  | N/A
3.5 | Laying - Box Culverts |  | Each culvert | Consecutive sections of box culverts are firmly placed butted together. The top section matched to the bottom section and no lips over adjoining bottom sections. Contact areas between the top and bottom sections mortared. Multi‑row box culverts laid with sections in each row in contact with the sections in the adjacent rows. | VicRoads Spec. Cl. 701.17(c) | Site Inspection | ITP signed | IP | Engineer | N/A |  | N/A
3.6 | Laying - Cutting of Culverts (If applicable) |  | Each culvert | When cutting culvert section to length or to create a penetration, cuts to be done by machine to achieve a clean vertical face. Any exposed reinforcement shall be coated with an approved epoxy treatment to prevent corrosion. | VicRoads Spec. Cl. 701.17(d) | Site Inspection | ITP signed | IP | Engineer | N/A |  | N/A
3.7 | Jointing |  | Each culvert | Rubber Ring Joints (RRJs) jointed with rubber rings which have been kept undisturbed, clean, and free from dirt and other foreign materials and shall be stored undercover if pipes are not to be installed immediately. RRJs assembled and prepared in accordance with the manufacturer’s recommendations. | VicRoads Spec. Cl. 701.18 | Document review/ Site Inspection | Manufacturer’s recommendations ITP signed | IP | Engineer | N/A |  | N/A
3.8 | Survey |  | Each Lot | The location of each run of underground drainage has been verified by a survey pickup prior to backfill and form the as constructed survey. Tolerances that apply: (a) offset of entry pits required to match lines of kerbs or barriers +/-20mm (b) plan location of pits other than offsets to kerb lines or barriers +/-100mm (c) Invert leve of pipes at pits +/-50mm whilst maintaining required drainage grade. (d) Departure from design grade of pipe runs +/-10mm in 10m provided minimum grade is not less than 1:250 | VicRoads Spec. Cl.701.10 | Survey | Survey Report | SCP | Engineer / Surveyor | N/A |  | N/A
3.9 | Backfilling |  | Each culvert | Culvert Under Area to be Paved: Where the trench has been excavated from design subgrade level or above, the trench is backfilled to design subgrade level with selected backfill material, and above that level with appropriate pavement material. Where the trench is excavated from below design subgrade level the trench is filled with selected backfill material. Culvert Under Area not to be Paved: The trench is backfilled with selected backfill material to a level 300mm above the top of the culvert and with ordinary backfill material above that level. | VicRoads Spec. Cl. 701.19(a) | Site Inspection | ITP signed | IP | Site Engineer | N/A |  | N/A
3.10 | Inlet/Outlet Structures |  | Each headwall | Inlet and outlet structures constructed in accordance with the drawings and specification. Concrete used for the construction of inlet and outlet structures shall comply with the requirements of Section 610. Footings extended to the depths shown on the drawings or as necessary to achieve a satisfactory foundation. If backfilling to the required level, select backfill material is used. | VicRoads Spec. Cl. 701.25 Cl.610 | Document Review/ Site Inspection | Latest IFC Drawing ITP signed | IP | Engineer | N/A |  | N/A
4 | Testing and Inspection
4.1 | Inspection of drainage lines |  | Each culvert prior to construction of pavement layers | All drainage lines beneath pavement inspected with CCTV cameras, after completion of earthworks to subgrade level and prior to construction of pavement layers. Inspections shall be conducted by an independent testing organisation using CCTV and reporting in accordance with WSA 05-2013 (Conduit Inspection Reporting Code of Australia). Reports provided to the Superintendent, with a copy of the CCTV and a summary of the loation of any defects detected. Any section of damaged pipe or box culvert which does not comply with Cl 701.31 is to be removed and where approved by the Superintendent, defects are to be reapirs inline with the previous. | Project Spec. Cl.3030.06 (k) VicRoads Spec. Cl. 701.30 and 701.31 | Site Inspection | Inspection Organisation Inspection report ITP signed | HP | Engineer / Superintendent |  |  | N/A
4.2 | Bedding Compaction Requirements |  | 3 test per lot. (1 lot consists of one layer of bedding for a culvert length between pits or endwalls) Min. 20% of all lots for each culvert shall be tested. | Bedding assessed for compaction and /or moisture in lots. Bedding compacted to refusal with handheld mechanical equipment with a mean moisture ratio of 92%. | VicRoads Spec. Cl. 701.20 (a) | Site Inspection | Compaction and moisture Test Records ITP signed | TP | Engineer | N/A |  | N/A
4.3 | Backfill Compaction and Moisture requirements |  | 3 test per lot. (1 lot consists of one layer of bedding for a culvert length between pits or endwalls) Min. 20% of all lots for each culvert shall be tested. | Backfill assessed for compaction and or moisture in lots. Backfill material which will have a nominal size after compaction of 40mm or < less compacted to a mean value of density ratio of not less than 97%. Backfill material which has a swell equal to or greater > than 2.5% maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. | VicRoads Spec. 701.20 (b) | Site Inspection | Compaction and moisture Test Records ITP signed | TP | Engineer | N/A |  | N/A
4.4 | Flushing System |  | Each culvert | Each culvert flushed clean from end to end on completion and maintained in proper working order. | VicRoads Spec. Cl. 701.28 | Site Inspection | ITP signed | IP | Engineer | N/A |  | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent
#