## 1145-C200-FUL-QAC-ITP-0001
|  |  | Inspection and Test Plan - Stripping Topsoil, Clearing and Grubbing | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-003
[11 empty] | Revision : 00 | 2025-05-05
Client: | Department of Transport & Planning |  | Construction Process: | Stripping Topsoil, Clearing and Grubbing |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Craigieburn Road Upgrade |  |  |  |  | Name: | Mustafa Kamel | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT31608 |  | Specifications: | Contract Specification DOT-31608 VicRoads Sections 201 (Jan 2016) |  | Senior Project Engineer |  | Delivery Manager |  |  | Delivery Manager
|  |  | Structure / Component: | Stripping Topsoil, Clearing and Grubbing
Date: | 2025-05-05 |  | Location: | Project wide |  | Date : |  | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Induction |  | Prior to Commencing Work | All personnel on site have been inducted to the CRG site | PMP Inductions Register | Document review | Site induction signed | AP | Site Engineer / Site Foreman | N/A
1.2 | Safety measures are in place, SWMS undertaken |  | Prior to Commencing Work | As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work. | Health and Safety Coordination Plan | Document Review | SWMS(s) signed | IP | Site Engineer, Site Foreman
1.3 | Check that current revision drawings are being used |  | Prior to Commencing Work | Refer to latest drawings and latest available revision used | IFC Project Drawings/ Drawing Register | Document review | Latest revision drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.4 | Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing Work | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | EMP, induction register Project Spec. Cl.1200.03 | Document review & Site inspection | Site induction signed This ITP signed | IP | Site Engineer | N/A
1.5 | Ground Penetration Permit (GPP) issued |  | Prior to Commencing Work | Current GPP signed and specific for the area where works will be executed. | GPP | Document review & Site inspection | GPP no. | HP* | Site Engineer | N/A |  | N/A
1.6 | Traffic Management (When required) |  | Prior to Commencing Work | Approved TMP and MOA | TMP | Document review & Site inspection | Approved TMP & MOA | AP | Site Engineer | N/A |  | N/A
1.8 | Extent of Clearing and Grubbing |  | Prior to Commencing Work | Extent of Clearing and Grubbing shall be within the limit of works and not more than the width required for completion of work under the contract | 201.04 | Site Inspection | Extent of Clearing and Grubbing reviewed by Superintendent | IP | Site Engineer |  |  | N/A
2 | Construction Works
2.1 | Identification of Cultural Heritage sites and areas of Cultural Significance |  | Prior to Excavation | Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing. Immediately stop work and notify the Superintendent if any Cultural Heritage is discovered or identified during construction. Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage. | Relevant EMP | Document review & Site inspection | Cultural Heitage approval (when required) Signed ITP | AP | Site Engineer | N/A |  | N/A
2.2 | Stripping of topsoil and grubbing of vegetation |  | Prior and after commencement of any ground disturbing activities | In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment. Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material | 201.05 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.3 | Removal of abandoned services |  | Prior to commencing this work | Removal and disposal of abandoned services and obsolete underground drainage lines which interfere with the execution of works has been done. Verify service is not likely to contain a hazardous material (sewage, asbestos pipe) Decommissioned services to be disposed of in a suitable manner. Decommissioned pits have been broken back to 0.3 metres below subgrade level. Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95% | 201.05 | Site Inspection | Signed ITP | HP* | Site Engineer | N/A |  | N/A
2.4 | Clearing of Trees and Vegetation |  | During clearing works | Clearing work shall not be undertake outside of the specified limits of work. Tree branches extending over the carriageway shall be trimmed by a suitably qualified arborist to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used. | 201.04 | Site Inspection | Signed ITP | HP* | Site Engineer | N/A |  | N/A
3 | Completion
3.1 | Disposal of vegetation |  | At completion of works | Tree trunks and large branches shall be removed from the site. Small tree branches, shrubs and leaves, excluding noxious weeds, shall be disposed of by chipping and mulching to form mulch. | VicRoads Spec. Cl.201.07 | Site Inspection | Delivery docket | IP | Site Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent