## ITP
|  |  | Inspection and Test Plan - Excavation, Fill with Type B & Subgrade Prep | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-004
[11 empty] | Revision : 00 | Date : 5/05/2025
Client: | Department of Transport & Planning |  | Construction Process: | Excavation, Fill with Type B & Subgrade Prep |  | Prepared by: |  | Reviewed by: |  |  | Approved by:
Project: | Melton Hwy/Leakes Road Upgrade |  | Specifications: | Project Specification DOT-31608 VicRoads Specification Sections 173 (Apr 2025) and 204 (Dec 2015) |  | Name: Mustafa Kamel |  | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT-31608 |  | Structure / Component: |  |  | Position: Senior Project Engineer |  | Position: | Delivery Manager |  | Position: | Delivery Manager
Date: | 2025-05-05 |  | Location: |  |  | Date : 5/05/2025 |  | Date : | 5/05/2025 |  | Date : | 5/05/2025
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminaries
1.1 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Excavation Permit issued |  | Prior to Commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review | Excavation Permit # | IP | Site Engineer | N/A |  | N/A
1.3 | Re-Use of insitu material |  | Prior to Placing fill | Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with clause 204.04. Type B Material shall meet the following requirements: CBR ≥ 1.5% Swell < 2.5%. Attach: Test Certificates | VicRoads Specification Cl. 204.04 Cl. 204.06 | Site Inspection | TestResults Material Category agreed with Superintendent | HP* | Site Engineer & Superintendent |  |  | N/A
1.4 | Type B Material Approval |  | Prior to Commencing | Prior to the import of Type B material, FH to provide the Superintendent, at least 1 week prior to the commencement of cartage, copies of test results to confirm that the proposed Type B material complies with section 204 of the VicRoads Spec. Type B Material shall meet the following requirements: CBR ≥ 2% Swell < 2.5%. If parameters are not met, remove 400mm of material mm below Cut Floor Level and replace with conforming Type B material. If removal and replacement of material below the Cut Floor Level is not required, surface shall be loosened to a depth of 150mm and re-compacted to meet the specified requirements. Attach: Test Certificates, Sample Delivery Dockets | VicRoads Specification Cl. 204.04(c) Cl. 204.06(e) | Site Inspection/ Document Review | Geotechnical Report | HP* | Site Engineer | N/A |  | N/A
2 | Cut Activities - 400mm below
2.1 | Survey set-out |  | Prior to Placing fill | Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used. The boxing width shall not be less than specified or shown on the drawings and the edges of boxing shall not deviate by more than 50 mm from the designed offset from the centreline or design line. | 204.03 | Site Inspection | Survey records & pegs on the ground | SCP | Site Engineer & Surveyor | N/A |  | N/A
2.2 | Ground water |  | Prior to Commencing (if required) | Where groundwater or seepage is encountered the Contractor shall notify the Superintendent and submit the proposed action to be taken to the Superintendent for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater. | VicRoads Specification Cl. 204.06(h) | Site Inspection/ Document Review | Area reviewed by Superintendent Signed ITP | HP | Site Engineer & Superintendent |  |  | N/A
2.3 | Acceptance of Rock Subgrade (when applicable) |  | Prior to construction of the regulating layer | Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance. Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review. | VicRoads Spec. Cl. 204.06(f) | Site Inspection/ Document Review | Superintendent acceptance Signed ITP | HP | Site Engineer & Superintendent |  |  | N/A
2.4 | Proof Roll - Cut Floor |  | Prior to Placing fill | Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling. Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling. No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent. Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review. Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent | VicRoads Spec. Cl. 204.12 Cl.173.03 Cl. 204.10(b) Cl. 204.07(d) | Site Inspection | Area visually reviewed by Superintendent Signed ITP | HP | Site Engineer & Superintendent |  |  | N/A
2.5 | Compaction Testing |  | Each Lot | Frequency = 6 tests per lot Min Frequency (subject to approval) = every second lot Lot = One day's production or 4,000m2, whichever is the lesser Characteristic Density Ratio = 97% minimum when more than 400mm below top of Type B Fill 99% minimum when within 400mm of top of Type B Fill Attach: NATA Compaction Test Report | Table 204.131 Section 204.13, 204.14 | Document Review | Sign ITP NATA Compaction Test Report | IP | Site Engineer | N/A |  | N/A
2.6 | Survey Pickup |  | Prior to Placing fill | Ensure the Cut Floor Level is recorded by survey | VicRoads Specification Cl. 204.03(f) Cl. 204.03(g) Table 204.031 | Document Review | Survey As-Built | SCP | Site Engineer & Surveyor | N/A |  | N/A
3 | Fill Activities
3.1 | Placement of Fill |  | Each Lot | Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness. Each layer shall be keyed in to the layer above by means of a textured surface Any rocky material present must be uniform throughout the layer. | VicRoads Spec. Cl. 204.10(d) | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.2 | Preparation of final surface - Subgrade |  | Prior to construction of subgrade layer | The top of the Type B material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03(g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water) | VicRoads Spec. Cl. 204.15 Cl. 204.03 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.3 | Trimming and level conformity |  | Each Lot (one day's production) prior to Commencing | Ensure that the level at any point on the surface of the Cut Floor Level immediately below capping does not differ by the mean values of more than 5 mm above or 15 mm below the specified level. The level at any point of the sugbrade shall not lie more than 20mm below a 3m straightedge in any direction excepting crowns. | VicRoads Specification Cl. 204.03(f) Cl. 204.03(g) Table 204.031 | Survey Report | Survey Record | SCP | Site Engineer & Surveyor | N/A |  | N/A
3.4 | Proof Roll - Top of fill layer |  | Prior to Placing fill | Areas upon which fills are to be constructed, all layers of fill, and material within 150 mm of the cut floor level in cuts, shall be test rolled in accordance with Section 173. Superintendent to be present during all test rolling. Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling. No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent. Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review. Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent | VicRoads Spec. Cl. 204.12 Cl.173.03 Cl. 204.10(b) Cl. 204.07(d) | Site Inspection | Area visually reviewed by Superintendent Signed ITP | HP | Site Engineer & Superintendent |  |  | N/A
3.5 | Post-compaction Testing |  | Each Lot | Post compaction testing shall meet the following requirements: CBR ≥ 1.5% Swell ≤ 2.5% Characteristic Density Ratio ≥ 99% Moisture Ratio ≥ 70% Subject to approval min frequency testing as follows: Compaction & Moisture: 1 test per 2 lots CBR & Swell: 1 test per 8 lots Attach: NATA Compaction Test Report | VicRoads Spec. Table 204.142 | Site Inspection | Signed ITP | TP | Site Engineer | N/A |  | N/A
3.6 | Survey Pickup - Top of subgrade |  | Prior to Placing fill | Ensure the Top of subgrade is recorded by survey | VicRoads Specification Cl. 204.03(f) Cl. 204.03(g) Table 204.031 | Document Review | Survey As-Built | SCP | Site Engineer & Surveyor | N/A |  | N/A
4 | LOT Closeout
4.1 | Survey As-Built |  | Each lot | The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Scale A: Min. No. of Measurements Per Lot: 80 Range x (mean) = +5, -15mm Max S (Standard Deviation) = 12 mm Attach: Survey As-builts / Survey Report | Section 204.03 (h), 204.16 | Review Document | Attach As-Built Report | SCP | Site Engineer & Surveyor | N/A |  | N/A
4.2 | Non-conformance Closure |  | Each Lot | Ensure All related Non-conformances are recorded and closed out. Enter: CAMS Case Number(s) [free text box] Attach: Closed NCR Report | Quality Management Plan | Review Document | This ITP | IP | Site Engineer | N/A |  | N/A
4.3 | Red Line Markups |  | Each Lot | Ensure any changes from design are captured in red-line markup drawings Enter: RFI References [free text box] | Quality Management Plan | Review Document | This ITP | IP | Site Engineer | N/A |  | N/A
4.4 | Final Inspection |  | Each Lot | It is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract. | Quality Management Plan | Review Document | This ITP | IP | Quality Manager | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date:
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent