## ITP
|  |  | Inspection and Test Plan - Fill with Material Type A | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-005
[11 empty] | Revision : 00 | Date : 05/05/2025
Client: | Department of Transport & Planning |  | Construction Process: | Fill with Material Type A |  | Prepared by: |  | Reviewed by: |  |  | Approved by:
Project: | Melton Hwy/Leakes Road Upgrade |  | Specifications: | Project Specification DOT-31608 VicRoads Specification Section 173 (Apr 2025) & 204 (Dec 2015) |  | Name: Mustafa Kamel |  | Name: Greg Grima |  |  | Name: Babak Rudd
Contract No: | DOT31608 |  | Structure / Component: |  |  | Position: Project Engineer |  | Position: Senior Project Engineer |  |  | Position: Quality Manager
|  |  | Location: | Project Wide |  | Date : 10/05/2022 |  | Date : 10/05/2022 |  |  | Date: 10/05/2022
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminaries
1.1 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Excavation Permit issued |  | Prior to Commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review | Excavation Permit # | IP | Site Engineer | N/A |  | N/A
1.3 | Type A Material Approval |  | Prior to Commencing | Prior to the import of Type A material, FH to provide the Superintendent, at least 1 week prior to the commencement of cartage, copies of test results to confirm that the proposed Type A material complies with section 204 of the VicRoads Spec. Type A Material shall meet the following requirements: CBR ≥ 6% Swell ≤ 1.5% Permeability ≤ 5e-9 PI (LL) = 6 - 25 PI x 0.425 passing ≤ 1000 Grading: % passing 75.0mm sieve = 100 % passing 4.75mm sieve = 40 - 80 % passing 0.075mm = 10 - 40 Attach: Test Certificates, Delivery Dockets Enter: Teambinder Approval number [free text box] | Project Specification Cl. 3020.05 VicRoads Specification Cl. 204.04(b) Cl. 204.06(c) Table 204.041 | Site Inspection | Approval # | HP* | Site Engineer & Superintendent | N/A |  | N/A
1.4 | Review of Subgrade Test Roll |  | Prior to Placing fill | No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent. Enter: Subgrade ITP Number [free text box] | VicRoads Spec. Cl. 204.12 Cl.173.03 Cl. 204.10(b) Cl. 204.07(d) | Site Inspection | ITP visually reviewed by Engineer Signed ITP | IP | Site Engineer & Superintendent | N/A |  | N/A
2 | Fill Activities
2.1 | Survey set-out |  | Prior to Fill | Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. IFC and latest available revision used. The boxing width shall not be less than specified or shown on the drawings and the edges of boxing shall not deviate by more than 50 mm from the designed offset from the centreline or design line. | Project General Specification Cl.1190.06 Latest IFC Drawings | Site Inspection | Survey records & pegs on the ground | SCP | Site Engineer & Surveyor | N/A |  | N/A
2.2 | Placement of Fill |  | Prior to Fill | Fill material shall be spread and compacted in layers not exceeding 200mm compacted thickness. Layers with a compacted thickness >200mm may be placed subject to approval from the Superintendent. Each layer shall be keyed in to the layer above by means of a textured surface Any rocky material present must be uniform throughout the layer. Enter: RFI Number [free text box] | VicRoads Spec. Cl. 204.10(d) | Site Inspection | Signed ITP | HP* | Site Engineer | N/A |  | N/A
2.3 | Preparation of final surface |  | Prior to placement of next layer | The level tolerances at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Surface is smooth, hard, tightly bound and free from depressions which are capable of holding water Surface is not to be more than 15mm or less than 30mm from what is specificed in IFC drawings | VicRoads Specification Cl. 204.15 Cl. 204.03(g) Cl. 173 VicRoads Specification Table 204.03(f) | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.4 | Proof Roll - Top of placed layer |  | Each Test Lot | Superintendent to be present during all test rolling. Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. No fill is to be placed on the prepared areas until the the area has been reviewed by the Superintendent. Where unsuitable material is encountered the Contractor shall propose in situ treatment and depth of excavation to the Superintendent for review. Where <10% of the lot area is deemed unsuitable, material shall be rectified as agreed by the Contractor and Superintendent | VicRoads Specification Cl. 204.12 Cl.173.03 | Site Inspection | Proof Roll Form signed. | HP | Site Engineer & Superintendent |  |  | N/A
2.5 | Post-compaction Testing |  | Each Lot | Type A Material shall be tested for the following: Characteristic Density Ratio ≥ 99% CBR ≥ 6% Swell ≤ 1.5% Permeability ≤ 5e-9 PI (LL) = 6 - 25 PI x 0.425 passing ≤ 1000 Grading: % passing 75.0mm sieve = 100 % passing 4.75mm sieve = 40 - 80 % passing 0.075mm = 10 - 40 Subject to approval min frequency testing as follows: Compaction & Moisture: 1 test per 2 lots CBR & Swell: 1 test per 2 lots Grading: 1 test for every second lot tested for compaction PI (LL): 1 test every 4 lots Permeability: 1 test every 4 lots Attach: Test Reports | Table 204.131 Section 204.13, 204.14 | Site Inspection | Attach Test Results | TP | Site Engineer | N/A |  | N/A
3 | LOT Closeout
3.1 | Survey As-Built |  | Each lot | The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point. Scale A: Min. No. of Measurements Per Lot: 80 Range x (mean) = +5, -15mm Max S (Standard Deviation) = 12 mm Attach: Survey As-builts / Survey Report | Section 204.03 (h), 204.16 | Review Document | Attach As-Built Report | SCP | Site Engineer & Surveyor | N/A |  | N/A
3.2 | Non-conformance Closure |  | Each Lot | Ensure All related Non-conformances are recorded and closed out. Enter: CAMS Case Number(s) [free text box] Attach: Closed NCR Report | Quality Management Plan | Review Document | This ITP | IP | Site Engineer | N/A |  | N/A
3.3 | Red Line Markups |  | Each Lot | Ensure any changes from design are captured in red-line markup drawings Enter: RFI References [free text box] | Quality Management Plan | Review Document | This ITP | IP | Site Engineer | N/A |  | N/A
3.4 | Final Inspection |  | Each Lot | It is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract. | Quality Management Plan | Review Document | This ITP | IP | Quality Manager | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date:
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent