## ITP
|  |  | Inspection and Test Plan - Unbound Pavements | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-006
[11 empty] | Revision : 00 | 2025-05-05
Client: | Department of Transport & Planning |  | Construction Process: | Unbound Pavements |  | Prepared by: |  | Reviewed by: |  |  | Approved by :
Project: | Melton Hwy/Leakes Road Upgrade |  | Specifications: | Contract Specification DOT-31608 VicRoads Specifications Section 173 (Apr 2025), 204 (Dec 2015), 304 (June 2023), 812 (July 2016) |  | Name: | Mustafa Kamel | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT31608 |  | Structure / Component: |  |  | Position: | Senior Project Engineer | Position: | Delivery Manager |  | Position: | Delivery Manager
|  |  | Location: | Project Wide |  | Date : | 2025-05-05 | Date : | 2025-05-05 |  | Date : | 2025-05-05
Lot No: | ITP-009-AX-LOT-XXX |  | Lot Title: | ITP-009-AX-LOT-XXX - Desc | Location: | From to |  | Lot Size/ Quantity: |  |  | Lot Opened Date:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Induction |  | Prior to Commencing | All personnel on site have been inducted to the CRU site | PMP Inductions Register | Document review | Site induction signed. | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environemental controls are in place |  | Prior to Commencing | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | EMP, Site induction, Project Specification Cl. 1200.03 | Document review & Site inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
1.4 | Safety measures are in place, Safe Work Method Statement (SWMS) undertaken |  | Prior to commencing | As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work. | Project General Specsefication Cl.1125.07 Health and Safety Coordination Plan | Document Review | SWMS(s) signed | HP* | Site Engineer | N/A
1.5 | Crushed Rock Mix design |  | Prior to Commencing Work | Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175. | VicRoads Specification Cl.812.04 | Document Review | Mix Design VicRoads Approval | HP | Superintendent |  |  | N/A
1.6 | Excavation Permit issued |  | Prior to Commencing Work | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review & Site inspection | Excavation Permit # | HP* | Site Engineer | N/A |  | N/A
1.7 | Traffic Management (When required) |  | Prior to Commencing Work | Approved TMP and MOA | TMP | Document review & Site inspection | Approved TMP & MOA | AP | Site Engineer | N/A |  | N/A
2 | Placing Fill
2.1 | Transverse Joints |  | Check prior to placing material | * Material should be spread to minimize number of joints. * Transverse joints shall be offset from one layer to next by not less than 2 metres * Transverse joints shall be offset from one layer to the next by not less than 2 m. | VicRoads Specification Cl.304.07 (a, b & c) | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.2 | Longitudinal Joints |  | Check prior to placing material | * Material should be spread to minimize number of joints. * longitudinal joints shall be offset from one layer to the next by not less than 150 mm. * longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane. | VicRoads Specification Cl.304.07 (a, d & e) | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.3 | Lot Size |  | Check prior to placing material | A single lot shall be considered a single layer of 4000m2 or one day's production in a single layer, whichever is lesser. For pavement construction, any lot that has a surface area less than 500 m2 may be treated as a small area and tested in accordance with Section 173. | VicRoads Specification Cl.304.08 (b)(ii & iv) Table 304.111 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.4 | Proof Roll |  | After placing material | Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent | VicRoads Specification Cl.304.08(b)(iv) Cl. 173 | Site Inspection | Signed ITP | HP | Site Engineer & Superintendent |  |  | N/A
3 | Testing and Inspection
3.1 | Determine Testing Scale & Initial testing frequency |  | Prior to Testing | Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement. Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111. | VicRoads Specification Table 204.161 VicRoads Specification Cl.304.08 (a) Cl.304.11 (b) Cl.304.11 (c)(i) Table 304.111 | Document Review/ Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.2 | Modified Compactive Effort |  | As per 3.1 | Characteristic Value of Density Ratio for Subbase:- > 98.0% for Scale A and >97.0% for Scale B. For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six. | VicRoads Specification Cl. 304.08 (b) (iii) Table 304.081 | Site Inspection | Test Records | TP | Site Engineer | N/A |  | N/A
3.3 | Permeability Testing |  | As per 3.1 | Class 4 Crushed rock max 5x10^-9 m/sec. Class 3 Crushed rock max 5x10^-7 m/sec Where the Class 4 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051 | Project Specification Cl.3040.05(a) Table 3040.051 | Site Inspection | Test Records from Supplier | TP | Site Engineer | N/A |  | N/A
3.4 | Post-compaction Plasticity Index |  | After compaction | Post- compaction Plasticity Index must comply with the requirement of table 3040.053. Calss 3: 0 < PI < 10. | Project Specification Cl.3040.05(a) Table 3040.053 | Site Inspection | Test Records from Supplier | TP | Site Engineer | N/A |  | N/A
3.5 | Post- compaction Grading |  | After compaction | The post compaction grading shall comply with the requirements of table 304.101 | VicRoads Specification Cl. 304.10 Table 304.101 | Site Inspection | Test Records from Supplier | TP | Site Engineer | N/A |  | N/A
3.7 | Survey Level |  | At completion | Scale A: - Minimum number of measurements per lot: 80 For Upper - Upper Subbase: Mean + 4mm to - 8mm with a maximum Standard Deviation of 8mm - Lower Subbase: Mean +6mm to -10mm with a maximum Standard Deviation of 10mm. - Base: Mean ± 5 with a maximum Standard Deviation of 8mm. | VicRoads Specification Table 304.061 Table 304.062 | Site Inspection | Test Records | TP | Site Engineer | N/A |  | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent