## ITP
|  |  | Inspection and Test Plan - Subsoil Drainage | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-007
[11 empty] | Revision : 00 | 2025-05-05
Client: | Department of Transport & Planning |  | Construction Process: | Subsoil Drainage |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melton Hwy/Leakes Road Upgrade |  |  |  |  | Name: | Mustafa Kamel | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT31608 |  | Specifications: | Project Specification DOT-31608 VicRoads Specifications Section 702 (May 2019) |  | Senior Project Engineer |  | Delivery Manager |  |  | Delivery Manager
|  |  | Structure / Component: | Subsoil Drainage
Date: | 2025-05-05 |  | Location: |  |  | Date : | 2025-05-05 | Date : | 2025-05-05 |  | Date : | 2025-05-05
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Material & Methodology Approvals
1.1 | Subsurface Drainage Pipes |  | Prior to Commencing Work | Ensure all subsurface drainage pipes ordered are Category 1: peroforated plastics Class 1000 and Precast concrete Class 2. All subsurface drainage pipes shall have a maximum perforation width of 1.5mm and a minimum length of 150mm/m2. | VicRoads Spec. Cl.702.04 | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.2 | Drainage Geotextile |  | Prior to Commencing Work | Type 2 drainage (NFC) Geotextile filter to meet requirements of a First Stage filter as per Table 702.061 | VicRoads Spec. Cl.702.061 | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.3 | SSD Backfill Material |  | Prior to Commencing Work | Type 2 and 3 backfill material types to be reviewed aginast specifcation and approved prior to ordering and use. Minimum testing requirements are reflected inline with 702.13. Type 2 NFC Grade B4 Filter Material Type 3 Sand Filter Grade A4 to A6 Filter Material. | Project Spec. Cl.3030.05(a) Table 702.131 | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.4 | Terminals & Pits |  | Prior to Commencing Work | Terminals and Pits Flushout Risers SD 1631 and Type S1 Pits reflect VR SD 1611. | SD 1611 Issue D SD 1631 Issue E | Document Review | This ITP signed | IP | Engineer | N/A |  | N/A
1.5 | Compaction Methodology |  | Prior to Commencing | Ensure compaction methodology of No Fines Backfill developed and submited for review prior. | VicRoads Spec. Cl.702.09(g) | Document review | This ITP signed | HP | Superintendent / Project Engineer |  |  | N/A
2 | Preliminary Works
2.1 | Check current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Foreman | N/A |  | N/A
2.2 | Excavation Permit issued |  | Prior to Commencing | Current Excavation Permit signed and specific for the area where works will be executed. Ensure DYBD Plans and Drawings relating to the particular area are available, current and where applicable higlights temporary services installed by Contractor | Excavation Permit | Document review | Excavation Permit # | HP* | Site Engineer | N/A |  | N/A
3 | Subsurface Drainage Works
3.1 | Suitability of Materials |  | Prior to placing drainage | Ensure subsurface drainage is not in contact with expansive materials (swell > 2.5%). For installation in expansive material, min. 100mm of compacted capping material is provided below the floor of the drainage trench. Ensure an adequate outlet is provided for existing drains. Drains that become redundant must be removed to ensure that water is not trapped. Refer below step. | Project Spec. Cl.3030.07(b) | Site inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.2 | Managing Existing Drainage |  | When placing drainage | Ensure removal and disposal of all reduntant pre-existing subsurface drainage assets. The area is backfilled with Type A material to subgrade or surface level. Where backfill is required above subgrade level, backfilling must be with pavement material that matches the pavement design for that pavement. | Project Spec. Cl.3030.07(c) | Site inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.3 | Excavation of Trench |  | When placing drainage | The base of the trench shall be sufficiently compacted and not more than 50mm below the invert level of the pipe to be placed. The top of any subsurface drainage pipe shall be at least 300 mm below the subbase and setuptfor the subsurface drain type. Grade of trench to be not flatter than 1 in 250 gradient. Base of the trench shall be inspected to verify compliance with the requirements prior to placing bedding in completed excavations. | VicRoads Spec. Cl.702.08 VicRoads Spec. Cl.702.09(a)(b) | Site inspection | Signed ITP | HP | Superintendent / Site Engineer |  |  | N/A
3.4 | Use of Geotextile |  | When placing drainage | Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contact with the wall when granular material is placed. The appropriate Subsurface Drainage Type 2 (B4 NFC filter) or Type 3 (Grade A4 to A6 filter) has been setup prior to backfill. | VicRoads Spec. Cl.702.08 | Site inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.5 | Installation of Subsoil Drainage |  | When placing drainage | Ensure bedding of thickness between 25-50mm is placed across the bottom of trench and graded to level. Pipes are firmly in place, slotted pipes positioned so openings are in lower half of the pipe. Flushout Risers, S1 Type Pits and Outlets are appropriate positioned to reflect the subsurface drainage design. | VicRoads Spec. Cl.702.09(d) | Site inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.6 | Placing of Granular Filter Material |  | When placing drainage | Filter socks must not be installed on subsurface drains backfilled with no fines concrete (Type 2). (HP) Filter material shall be moistened and compacted with minimal disturbance to pipes. The loose thickness of layers shall not exceed 300 mm. For Type 2 (NFC) No-fines concrete shall be placed and compacted within 1 hour of mixing. | VicRoads Spec. Cl.702.09(g) Project Spec. Cl.3030.05(b) | Document Review | Signed ITP | IP | Site Engineer / Foreman |  |  | N/A
3.7 | Installation of Subsurface Outlet marker posts (If required) |  | After drainage is placed | Marker posts installed at all subsurface outlets, and must be 75 mm diameter x 1500mm treated pine inserted 600mm into the ground. | Project Spec. Cl.3030.07(b) | Site inspection | Signed ITP | WP | Site Engineer / Foreman | N/A |  | N/A
3.8 | Flushing Test |  | After drainage is placed | Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. | VicRoads Spec. Cl.702.09(h) | Site inspection | Signed ITP/ Record of flushing tests | WP | Superintendent / Site Engineer |  |  | N/A
3.9 | Inspection and Completion |  | After drainage is placed | All subsurface drainage lines constructed shall be inspected, after completion of the flushing test as stated in clause 702.09(h) and prior to placement of asphalt, by an independent testing organisation using closed circuit television (CCTV), Verify that the flow of water is not obstructed by waste construction material left inside and to check for visible signs of defects. Placement of apshalt cannot proceed until after this inspection. CCTV is completed, damaged or deformed drainage pipe removed and replaced. Along with waste and defect free condition of lines verified by the Superintended. | VicRoads Spec. Cl.702.09(h) | Site inspection | Signed ITP/ Record of flushing tests | HP | Superintendent / Site Engineer |  |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent