## CRU-FH-ITP-0011
|  |  | Inspection and Test Plan - Kerb and Channel (Supply & Install) | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-008
[11 empty] | Revision : 00 | 2025-05-05
Client: | Department of Transport & Planning |  | Construction Process: | Kerb and Channel (Supply and Install) |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melton Hwy/Leakes Road Upgrade |  | Specifications: | Contract Specification DOT-31608 VicRoads Specification Sections VicRoads Section 703 (24/08/2021) VR SD2001 VR SD2102 AS 2876 AS1379 |  | Name: | Mustafa Kamel | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT31608 |  | Structure / Component: |  |  | Position: | Senior Project Engineer | Position: | Delivery Manager |  | Position: | Delivery Manager
|  |  | Location: |  |  | Date : | 2022-05-05 | Date : | 2022-05-05 |  | Date : | 2022-05-05
Lot No: CRU-ITP0012-LOT- |  |  | Lot Title: |  | Location: From ( ) to ( ) |  |  | Lot Size/ Quantity: |  |  | Lot Opened Date:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Mix design |  | Prior to commencing | Approved VR mix design to be used. Concrete being placed via extrusion machines have minimum cement content of 320 kg kg/m3 Where K&C is placed and compacted with internal vibration between previously placed formwork, concrete shall be: N32 portland cement–based concrete | SD2001 AS1379 Section 703.05, 703.06, 703.07 | Document Review | ITP signed/Mix Design Certificate | HP | Site Engineer & Superintendent |  |  | N/A
1.3 | Bedding Material |  | Prior to commencing | Bedding shall be size 20 mm Class 3 or Class 4 crushed rock or Class 3 or Class 4 crushed concrete, manufactured and supplied in accordance with Sections 812 or 820 respectively. | Section 703.21 IFC Drawings | Verify | Material Conformance Certificate | HP* | Site Engineer | N/A |  | N/A
1.4 | Curing Compound |  | Prior to commencing | Curing compound shall comply with AS3799 | Section 703.10 | Verify | Material Conformance Certificate | HP* | Site Engineer | N/A |  | N/A
1.5 | Temporary drainage provisions |  | Prior to commencing | If obstructing waterways ,culverts or channels, temporary diversion of discharge of drainage and storm water to be in place. Need to obtain prior written approval from the relevant waterway authority prior to diversion. | Section 703.18 | Visual inspection | ITP signed | HP* | Site Engineer / Site Foreman | N/A |  | N/A
2 | Construction / Installation Activities
2.1 | Setting out |  | Prior to start | Set out work in accordance with drawing. The superintendent will review and confirm set out. The work shall be constructed in accordance with the confirmed set out to the line and level and cross-sectional profiles as shown on the drawings. | Section 703.17 | Site Inspection | ITP signed | HP | Site Engineer & Superintendent |  |  | N/A
2.2 | Bedding |  | Each lot | Bedding to be compacted to a thickness of not less than 100mm . Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted . | Section 703.21 | Site Inspection | ITP signed | WP | Site Engineer & Superintendent |  |  | N/A
2.3 | Formwork |  | Each lot | Joints in formwork shall be constructed such that loss of mortar is prevented. Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation. | Section 703.12 AS3610 | Site Inspection | ITP signed | WP | Site Engineer & Superintendent |  |  | N/A
2.4 | Pre Pour Check |  | Each lot | Bedding shall be moist but shall have no free water on the surface . Concrete shall not be placed when the air temperature measured at the point of placement is > 35°C or < 5°C | Section 703.09 Section 703.21 Section 610.17a), b) & c) | Site Inspection | ITP signed Ambient temperature-----°C | HP*/WP | Site Engineer/Site superintendent |  |  | N/A
2.5 | Concrete placement |  | Each lot | Temperature of concrete to be measured immediately prior to placing and shall not be less than 10°C or greater than 32°C. Concrete is to be satisfactorily compacted so that finished surface are free from surface pitting larger than 5mm diameter, honey combing or faulty patches. Fresh concrete shall not be placed against concrete which has taken its initial set, except at properly formed construction joints. Machine Extrusion: Concrete is to be fed to extrusion machine at a uniform rate. | Section 703.08 Section 703.23 | Site Inspection | ITP signed Concrete Temperature ---°C | IP | Site engineer | N/A |  | N/A
2.6 | Transitions |  | Each lot | Where it is necessary to join to an existing section of profile different from that being constructed, the change of profile shall be made at a constant rate between 10 and 20 mm per metre. | Section 703.24 | Site Inspection | ITP Signed | IP | Site engineer | N/A |  | N/A
2.7 | Surface Finish |  | Each lot | All edgings shall be rendered to a thickness not exceeding 3mm and trowel finished. Renderings shall be applied within 30 minutes of extrusion. Concrete to have a neat appearance and uniform colour. Class 3 finish required for external surfaces. Class 4 finish required for permanently hidden surfaces. | Section 703.25 | Site Inspection | ITP signed | IP | Site Engineer/ Site Forman | N/A |  | N/A
2.8 | Formwork Stripping |  | Each lot | Formwork shall not be stripped before the minimum time of: - External faces 2 days - Permanently hidden faces 1 day | Section 703.12 AS3610 | Site Inspection | ITP signed | IP | Site Engineer/ Site Forman | N/A |  | N/A
2.9 | Tolerance |  | Each lot | Match existing surfaces to within 5 mm from dimensions shown on drawings. Section dimensions to be with in 5mm and 15 mm for width , for dimension less than 25mm tolerance to be ±3mm. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance 0 to +10mm. Except on curves or sharped areas, the deviation of the finished work from a 3m straight edge shall not exceed 5mm at any point. | Section 703.15 | Site Inspection | ITP signed | IP | SITE Engineer/surveyor | N/A |  | N/A
2.10 | Curing |  | Each lot | The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed. Concrete edgings shall be cured for a period of not less than three days after placing the concrete | Section 703.10 | Site Inspection | ITP signed | IP | Site Engineer/Site Foreman | N/A |  | N/A
2.11 | Joints |  | Each joint | Transverse joints constructed at intervals not exceeding 2.5m. Groove cut 20mm deep and > 5mm wide on exposed surfaces, following with a vertical cut made through the base of the groove (depth >50mm from surface of section). Bonding between the concrete paving or shared use path and the edging shall be prevented by painting the back of the edging with bitumen, or by using a strip of bituminous felt material between the edging and the concrete paving or shared use path. | Section 703.26 | Site Inspection | ITP signed | IP | Site Engineer / Site Forman | N/A |  | N/A
2.12 | Backfilling |  | Each lot | No earlier than 3 days after casting, top soil material free from perishable matter, lumps or balls of clay, shall be placed and firmly compacted behind the edging in layers not > 150m thick and to a width not < 300mm behind the edging to the top of the edging. | Vic Road spec 703.29 | Site Inspection | ITP signed | IP | Site Engineer | N/A |  | N/A
2.13 | Protection of Concrete |  | Each lot | All concrete shall be protected from damage from early loading. | Section 703.27 | Site Inspection | ITP signed | IP | Site Engineer | N/A |  | N/A
2.14 | Cracking of Concrete |  | Each lot | The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm. Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687 | Section 703.30 | Site Inspection | ITP signed | IP | Site Engineer | N/A |  | N/A
3 | Post-construction / Post-installation Activities
3.1 | Survey Conformance |  | Completion of each lot | Survey to as built the works and to confirm the works are within the specified tolerances. | Section 703.15 | Document Review | As-built survey records | WP | Project Engineer/ Surveyor | N/A |  | N/A
3.2 | Non-conformance Report (NCR) Closure |  | Once, prior to closure of this lot / element / Work area | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Quality Management Plan | Document Review | This ITP | HP* | SE/PE/SPE | N/A |  | N/A
3.3 | Red lines |  | Once, prior to closure of this lot | All RFI's and deviations from drawing to be marked in accordance with CRU red line markup procedure | Quality Management Plan | Document Review | This ITP | HP* | SE/PE/SPE | N/A |  | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent