## ITP
|  |  | Inspection and Test Plan - Asphalt Placement | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-009
[11 empty] | Revision : 00 | 2025-05-05
Client: | Department of Transport & Planning |  | Construction Process: | Asphalt Placement |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melton Hwy/Leakes Road Upgrade |  | Specifications: | Contract Specification DOT-31608 VicRoads Section 407 (July 2023) |  | Name: | Mustafa Kamel | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT31608 |  | Structure / Component: | Pavement |  | Position: | Senior Project Engineer | Position: | Delivery Manager |  | Position: | Delivery Manager
|  |  | Location: | Project Wide |  | Date : | 2025-05-05 | Date : | 2025-05-05 |  | Date : | 2025-05-05
Lot No: |  |  | Lot Title: |  |  |  |  | Lot Size/ Quantity: |  |  | Lot Opened Date:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent (MRPV) | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Submission of Mix Design |  | Prior to commencing paving | Ensure this mix design has been registered and is approved by Superintendent prior to laying mix. | VicRoads Spec. Cl.407.06 | Correspondence of receipt of mix design | VR approval Completed ITP | HP | Site Engineer/ Asphalt Supervisor / Superintendent
1.2 | Ensure underlying lot conforms |  | Prior to Commencing | All quality information received for lot (includes levels, area and volume) and NCRs (BIRs) approved. | Relevant ITP for underlying lot | Document review | Inspection and Test Plan | HP* |  | N/A
1.3 | Visual Inspection of underlying lot |  | Prior to Commencing | If the execution of any part of the work under the Subcontract is dependent upon the quality and completeness of an existing surface or work performed by Separate Contractors, the subcontractors shall visually inspect the existing surface or Separate Contractor's work for matters including the following: (i) Homogeneous surface and pavement material (ii) Uniform in texture (iii) Free from tearing and scabbing (iv) Free from laminations (v) Free from loose and foreign materials and immediately notify the Contractors Representative of all matters discovered that a competent contractor who specialises in the type of works performed under Subcontract should have discussed by such inspection which in the Subcontractor's opinion render such work unsuitable for the proper execution of the work under the Subcontract. | Relevant ITP for underlying lot | Visual Inspection | Inspection and Test Plan ITP Signed | WP | Site Engineer/ Asphalt Supervisor | N/A
1.4 | Ambient Conditions for Placing |  | Prior to commencing paving | The majority of the surface area to be paved has a temperature greater than or equal to the following: Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600 Wearing Courses: 10°C for conventional binders or 15°C for PMBs | 407.13 | Verify | Thermometer / gauage | IP | Site Engineer/ Asphalt Supervisor | N/A
1.5 | Planning of Joints |  | Prior to commencing paving | Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client (MRPV): (i) Transverse Joints Offset from layer to layer by at least 2m (ii) Longitudinal Joints Offset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. (iii) Wearing course shall be on lane lines. | 407.17 (b) & (c) Pavement Drawings | Measure and mark out runs by tape measure or survey | Paving Plan | WP | Project Engineer/ Asphalt Supervisor Superintendent
1.6 | Longitudinal Joints with existing Pavement |  | Prior to commencing paving | Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm. Depth of step to be cut to the full depth of each indiviual layer. | 407.16 (c) Project Specs. Section 3040.06 (d)(vii) | Visual Inspection | ITP Signed | WP | Project Engineer/ Asphalt Supervisor | N/A
2 | Asphalt Placement
2.1 | Commencement of placement |  | Prior to commencing Paving | Approval to place asphalt on the sub-base or granular base for a new pavement or for an ordinary of an existing bituminous surfaced pavement. | 404.13 405.07 407.18 | Visual Inspection | Inspection and Test Plan | HP | Site Engineer/ Asphalt Supervisor / Superintendent
2.2 | Cold Weather Placement Management Plan |  | Prior to commencing Paving (Seasonal) | Prior to commencing cold weather placement of asphalt, the Contractor shall submit a job specific cold weather placement management plan to the Superintendent for review. | 407.17C | Document review | Inspection and Test Plan | HP* | Project Engineer/ Asphalt Project Manager or Engineer | N/A
2.3 | Mix Design Confirmation |  | Each lot | Check correct mix design as per pavement design has been delivered prior to laying mix. | VicRoads Spec. Cl.407.06 | Visual Inspection & Delivery Docket | Delivery docket Completed ITP | HP* | Site Engineer/ Asphalt Supervisor | N/A
2.4 | Running traffic on Placed Asphalt |  | During Construction | Traffic not to be placed on asphalt placed until Fulton Hogan agree the surface temperature is less than the required mix temp. (SMA 40°C) to receive traffic. | 404.14 | Verify | Inspection and Test Plan ITP Signed Thermometer / gauage | HP* | Site Engineer/ Asphalt Supervisor | N/A
3 | Testing
3.1 | Placing Material |  | Per Lot | 407.21 - DGA as per 407.22 405.08 - RGG - not less than 3 passes with steel wheeled roller. 3 passes to be made within time to compaction cessation substrate (pavement) temperature is between 7° and 10°C. | 407.21 405.08 404.14 417.12 | Material Sampling & testing | Visual Inspection/ Compaction test results Visual Inspection/ Visual Inspection/ Field Report/ | WP | Site Engineer/ Asphalt Supervisor Superintendent | N/A
3.2 | Survey Level Conformance |  | Per 4,000m2 at completion of work | 407.293 Surface Level Tolerances for Sub-base and Pavement Courses Scale of Surface Level Measurement - Granular or CT Subbase Asphalt Layers Range (mm) Max S. (mm) Range (mm) Max S. (mm) Scale A - +4 to -8 8 +/- 5 8 Scale B - +6 to -12 13 +/- 8 10 | VicRoads Sec 407.293 Surface Level Tolerances for Sub-base and Pavement Courses | Document Review/ Site Inspection | Survey Conformance Report | SCP | Site Engineer/ Surveyor / Survey Manager | N/A |  | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent
Note on K15: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on K17: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on K19: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on K22: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on K23: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on K26: Rodrigo Anchico: Write "N/A" to disable the cell.
Note on K27: Rodrigo Anchico: Write "N/A" to disable the cell.