## ITP
|  |  | Inspection and Test Plan - Permanent Line Marking | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-013
[11 empty] | Revision : 00 | 2025-05-05
Client: | Department of Transport & Planning |  | Construction Process: | Permanent Line Marking |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melton Hwy/Leakes Road Upgrade |  |  |  |  | Name: | Mustafa Kamel | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT31608 |  | Specifications: | Contract Specification DOT-31608 VicRoads Specification Section 721 (Feb 2017) |  | Position: | Senior Project Engineer | Position: | Senior Project Engineer |  | Position: | Senior Project Engineer
|  |  | Structure / Component: | Linemarking works |  | Date : | 2025-05-05 | Date : | 2025-05-05 |  | Date : | 2025-05-05
Lot No: |  |  | Lot Title: |  | Location: From ( ) to ( ) |  |  | Lot Size/ Quantity: |  |  | Lot Opened Date:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Inductions |  | Prior to Commencing linemarking works | All personnel on site have been inducted to the CRU Site. | Inductions Register | Document review | ITP signed Site induction signed. | IP | Site Engineer / Site Foreman | N/A
1.2 | Safety measures are in place, SWMS undertaken |  | Prior to Commencing linemarking works | As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work. | Health and Safety Co-Ordination Plan | Document Review | ITP signed SWMS(s) signed | IP | Site Engineer / Site Foreman | N/A
1.3 | Check that current revision drawings are being used |  | Prior to Commencing linemarking works | Issued For Construction (IFC) drawings, & latest available revision used. | IFC Project Drawings, | Document review | ITP signed Latest revision IFC drawings | IP | Site Engineer / Site Foreman | N/A
1.4 | Confirm understanding of current EMP related to the work area and that all prescribed environemental controls are in place |  | Prior to Commencing linemarking works | All environmental measures to be implemented as per construction environmental management plan | CEMP, Site induction, | Document review & Site inspection | ITP signed | IP | Site Engineer / Site Foreman | N/A
1.5 | Traffic Management (When required) |  | Prior to Commencing linemarking works | Approved TMP and MOA in use | Applicable TMP | Document review & Site inspection | ITP signed, Approved TMP & MOA | IP | Site Engineer / Site Foreman | N/A
2 | Linemarking Works
2.1 | Verification of line marking material |  | Prior to commencing site preparation | Line marking material to comply with minimum requirements as specified in VicRoads Spec 721.A05, VR721.A13, VR721.A14, & PS3070.05 | VR721.A05 | Document review | ITP signed Material compliance | IP | Site Engineer | N/A
2.2 | Site preparation |  | Per lot | Site to be prepared by removing any foreign materials and debris within reasonable limits. | VR721.A06, VR721.A08 | Document review & Site inspection | ITP signed | IP | Site Engineer | N/A
2.3 | Removal of unsuitable/redundant markings (If required) |  | Per lot | If redundant/unsuitable pavement markings to be removed, removal methodology to be approved by superintendent | VR721.A06, VR721.A08, VR721.A12 | Document review & Site inspection | ITP signed | HP | Site Engineer / Superintendent |  |  | N/A
2.4 | Set out of line markings; dimensions and spacings |  | Per lot | Painting/application of material shall not commence until the Superintendent has inspected the setout and installation timeframes are adherred to. | IFC Drawings, VR721.A09, VR721.B05, VR721.B04 | Document review & Site inspection | ITP signed Consent to proceed by Superintendent OR written exemption granted | HP | Site Engineer / Superintendent |  |  | N/A
2.5 | Painted pavement marking application (if required) |  | Per lot | If required, Council approved painted pavement marking is to be applied by a self propelled machine, with the minimum requirements for paint, glass, and skid resistance to be as per Material TDS | Material TDS | Document review & Site inspection | ITP signed | IP | Site Engineer | N/A
2.6 | Long life pavement marking application |  | Per lot | all line marking shall be applied using a self propelled ride-on machine including statcon marking unless otherwise approved, with the minimum requirements for long life materials and glass beads to be as per table 721.E021 & Material TDS | VR721.E01 VR721.E02 Material TDS | Document review & Site inspection | ITP signed | IP | Site Engineer | N/A
2.7 | Protection of works |  | Per lot | Work to be protected by appropriate means until it is trafficable. | VR721.A11 | Document review & Site inspection | ITP signed | IP | Site Engineer | N/A
3 | Testing
3.1 | Acceptance of retroflectivity |  | Per lot | Contractor to measure level of retroflectivity, with the average of six test site retroflectivity values for each lot. | VR721.A13 | Document review & Site inspection | ITP signed Test report | TP | Site Engineer | N/A
3.2 | Acceptance of colour |  | Per lot | Colour match tests for white & yellow markings to be conducted as per 721.A14, with results forwarded to the superintendent no later than 5 days from testing. | VR721.A14 | Document review & Site inspection | ITP signed Test report | TP | Site Engineer | N/A
3.3 | Acceptance of tolerances |  | Per lot | Survey conformance report to show line marking applied as per tolerances shown in table 721.A101. | VR721.A10 VR721.A101 | Document review & Site inspection | ITP signed Survey report | SCP | Site Engineer | N/A
3.4 | Acceptance of work |  | Per lot | Work to comply with specified requirements as detailed in VR721.A12 | VR721.A12 | Document review & Site inspection | ITP signed | TP | Site Engineer | N/A
3.5 | Records & reporting |  | Per lot | All new markings to have job completion report forwarded to the superintendent, with a retroflectivity report completed and forwarded to the superintendent showing the retroflectivity for each test lot. | VR721.B06 | Document review & Site inspection | ITP signed Reports | TP | Site Engineer | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Work Completed On:
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent