## ITP
|  |  | Inspection and Test Plan - Permanent Roadside Signage | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-014
[11 empty] | Revision : 00 | 2025-05-05
Client: | Department of Transport & Planning |  | Construction Process: | Permanent Roadside Signage |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melton Hwy/Leakes Road Upgrade |  |  |  |  | Name: | Mustafa Kamel | Name: | Greg Grima |  | Name: | Greg Grima
Contract No: | DOT31608 |  | Specifications: | Contract Specification DOT-31608 VicRoads Specification Section 714 (Aug 2019), 860 |  | Senior Project Engineer |  | Delivery Manager |  |  | Delivery Manager
|  |  | Structure / Component: | Roadside Signage
|  |  | Location: | Project Wide |  | Date : | 5/05/2025 | Date : | 5/05/2025 |  | Date : | 5/05/2025
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Inductions |  | Prior to Commencing | All personnel on site have been inducted to the CRG Site. | PMP Inductions Register | Document review | Site induction card | AP | Site Engineer / Site Foreman | N/A
1.2 | Safety measures are in place, SWMS undertaken |  | Prior to Commencing Work | As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work. | Health and Safety Co-Ordination Plan | Document Review | SWMS(s) signed | HP* | Site Engineer, Site Foreman & Superintendent | N/A
1.3 | Check that current revision drawings are being used |  | Prior to Commencing Work | Issued For Construction (IFC) and latest available revision used | IFC Project Drawings/ Drawing Register | Document review | Latest revision IFC drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.4 | Confirm understanding of current EMP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | EMP, Site induction, | Document review & Site inspection | ITP signed | IP | Site Engineer | N/A
1.5 | Traffic Management (When required) |  | Prior to Commencing Work | Approved TMP and MOA | Applicable TMP no.: | Document review & Site inspection | Approved TMP & MOA | AP | Site Engineer | N/A |  | N/A
2 | Roadside Signage Install
2.1 | Set out posts and foundations |  | Prior to commencing install | The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences. | VicRoads Spec. Cl.714.06 | Document review & Site inspection | Consent to proceed by Superintendent OR written exemption granted This ITP signed | HP | Site Engineer / Superintendent |  |  | N/A
2.2 | Material compliance |  | Prior to commencing install | All road Signing must comply with the Technical References including the requirements of section 860 of the VicRoads Standard Specification Sections for Roadworks and Bridgeworks. | VicRoads Specification 860 | Document review | Material compliance This ITP signed | IP | Site Engineer | N/A
2.3 | Installation method |  | Once per lot | The sign installation shall be as described in the sign schedule and as shown on the contract drawings. | VicRoads Specification 714.04 & 07 | Document review & Site inspection | This ITP signed | IP | Site Engineer | N/A
2.4 | Installation tolerances |  | After completion of works | Verify signs were installed to tolerances stated in VicRoads Sec. 714.05 | VicRoads Specification 714.05 | Document review | Photos This ITP signed | IP | Site Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent