## ITP
|  |  | Inspection and Test Plan - Installation of Traffic Signals | [7 empty] | Document # DOT-31608-FUL-QAC-ITP-016
[11 empty] | Revision : 00 | 2025-05-05
Client: | Department of Transport & Planning |  | Construction Process: | Installation of Traffic Signals |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | Melton Hwy/Leakes Road Upgrade |  | Specifications: | Department of Transport Specification Section 730 |  | Name: Mustafa Kamel |  | Name: Greg Grima |  |  | Name: Greg Grima
Contract No: | DOT31608 |  | Structure / Component: |  |  | Position: SPE |  | Position: Delivery Manager |  |  | Position: Delivery Manager
|  |  | Location: |  |  | Date : 5/5/25 |  | Date : | 2025-05-05 |  | Date :5/5/25
Lot No: |  |  | Lot Title: |  | Location: |  |  | Lot |  |  | Lot Opened Date:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Induction |  | Prior to Commencing | All personnel on site have been inducted to the CRG site | PMP Inductions Register | Document review | Site induction signed. | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Confirm understanding of current Environment Management Plan (EMP) related to the work area and that all prescribed environemental controls are in place |  | Prior to Commencing | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | EMP, Site induction, Project Specification Cl. 1200.03 | Document review & Site inspection | Signed ITP | IP | Site Engineer | N/A
1.4 | Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken |  | Prior to commencing | As per Fulton Hogan Safety Strategy. All personnel on site to have signed onto relevant SWMS before commencing work. | Health and Safety Co-Ordination Plan | Document Review | SWMS(s) signed | IP | Site Engineer & /Site Foreman | N/A
1.5 | Ground Penotration Permit issued |  | Prior to Commencing Work | Current Ground Penotration Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review & Site inspection | Excavation Permit # | HP* | Site Engineer | N/A |  | N/A
2 | Installing Traffic Signals
2.1 | Civil Works |  | Following Preliminary Works | Works completed and subcontractor DoT Report completed in accordance with Section 730 & 733 of the Department of Transport Specification Pre-installation meeting conducted HP Sec 730.08 c -DoT Pre-Installation Report Alternative foundations noted in Pre-Installation Report HP Sec 730.11-DoT Pre-Installation Report Proposed boring to be discussed, agreed and noted on Pre-installation report HP Sec 733.03 - DoT Pre-Installation Report Pre backfill inspections (conduit / foundation) carried out and signed off HP Sec 730.11, HP Sec 733.03, HP Sec 733.06 Pit lid Surround prepour inspection HP Sec 733.07 (c) Grouting of bores to be inspected HP Section 733.03 Concrete testing completed (Slump and Compressive Strength) In accordance with Section 610.16 | (DoT) Pre-Instalation Report | Document review & Site Inspection | Signed Pre-Installation Report Completed Healey's ITP FO41 Pit, Conduit, Foundation Installation Concrete test reports | HP* | Site Engineer & Sub-contractor | N/A
2.2 | Electrical Works |  | Following Civil Works | Works completed and subcontractor DoT Report completed in accordance with Section 730 of the Department of Transport Specification 1) Traffic hardware inspected HP Sec 730 14 - DoT Pre Comissioning Report. 2) Cabling Scheme agreed HP Sec 730.17 - DoT Pre Comissioning Report. 3) Electiral Tests & Flash Test performed HP Sec 730.17 -DoT Continuity, Insulation, Pre-comissioning Reports, -HEALEYS - FO83 TSIR Electrical Checklist Inspection & Test Plan | (DoT) Continuity Report (DoT) Insulation Resisitance Report (DoT) Pre-commissioning Report | Document review & Site Inspection | Signed & DoT Reports Concrete test reports. | HP* | Site Engineer & Sub-contractor | N/A
3 | Completion of Works
3.1 | Completion of Traffic Signal Works |  | Upon Completion of all Works | Works completed and subcontractor ITP completed in accorandance with Section 730 of the Department of Transport Specification | (DoT) Comissioning Report (DoT) Power Consumtion Report | Document review & Site Inspection | Signed ITP | HP* | Project Engineer / Site Engineer | N/A
Notes
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
[5 empty] | WP | Witness Point |  | An inspection which must be witnessed by the Superintendent