## Table 1
INSPECTION TEST PLAN CONSTRUCTION
Foreman |  |  | Nigel Renton Kate Gentle Josh Faulkner Rob Hayes |  |  |  | Action | Morell-Nelson Foulsewer Renewal
Contractor's Representative | [7 empty] | W |  |  | Witness | Stage 1 - Morell Street, Nelson Street between Hardy Street and Martin Street
Contract Manager | [7 empty] | H |  |  | Hold Point
Engineer | [7 empty] | M |  |  | Monitor | Job Number: |  | 4814 | Version:
No: | Detail |  |  |  | Inspection / Test Point |  | ACTION | Conformance Criteria (Whats Required) |  |  | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments
1 | ITP sign off |  |  |  | Sign off |  | H | Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed. |  |  | Prior to commencement | Review | Sign This ITP | Divisional Manager
2 | Materials testing to be provided to Engineer for acceptance |  | SR10.103 |  | Aggregate Acceptance |  | W | Laboratory test certificates: MDD and Grading Results |  |  | Prior to commencement | Lab report | Sign This ITP | Contractor's Rep
3 | Ensure Approved Plans are on site. Safety/Environmental/Quality/TMP/Permits/Site Plans |  |  |  | Review |  | W | All plans permits produced under pre-construction available on site at all times |  |  | Prior to commencement | Review | Sign This ITP | Contractor's Rep
4 | Notice to Engineer Reviewed by Contract Manager |  |  |  | Review |  | W | All NTE's to be reviewed |  |  | Prior to submission to Engineer | Review | Sign This ITP | Contractor's Rep
5 | Variations Reviewed by Contract Manager |  |  |  | Review |  | W | All Variations to be reviewed |  |  | Prior to submission to Engineer | Review | Sign This ITP | Contractor's Rep
6 | Site Pre-Condition Inspection |  | D1.5, D1.32.4 |  | Review |  | W | Record existing condition of site via walk-over/drive-over |  |  | Prior to excavation | Video | Sign This ITP | Contractor's Rep
7 | Powernet and Chorus locates completed |  | D1.8 |  | Inspection |  | H | All known services have been located, reference back to plans to ensure everything has been located |  |  | Prior to excavation | Inspection | Sign This ITP | Supervisor/Foreman
8 | Material inspection |  | D2, D2.4.1 |  | Material Inspection |  | W | Complete inspection of materials as they arrive to site |  |  | Upon pipe delivery | Inspection | Sign This ITP | Supervisor/Foreman
9 | Sewerage continuity |  | C1.13, D2.7.5 |  | Monitoring |  | W | Ensure there is continuity in sewerage network during construction works |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman
10 | Existing alignment markout |  | D2.7.1, C1.14 |  | Inspection/Test Point |  | H | Markout existing aligment and trench edges onsite, to be confirmed by the Engineer's Rep |  |  | Prior to commencement | Inspection | Sign This ITP | Supervisor/Foreman
11 | Inspect subgrade |  | D13.4.3, D13.4.4 |  | Inspection/Scala |  | M | Inspect subgrade as expose, complete scala if required. Contact manager for further instruction if subgrade is deemed unsuitable |  |  | During construction | Inspection/Scala | Sign This ITP | Supervisor/Foreman
12 | Pipe laying |  | D2, D2.7, D2.11.2 |  | Pipe laying |  | M | Pipe to be laid as per specification, contract document and plans |  |  | During construction | Spot checks | Sign This ITP | Supervisor/Foreman
13 | Saddles onto main, for laterals |  | D4 |  | Sign off |  | W | Install as per construction plans |  |  | During construction | Photos | Sign This ITP | Supervisor/Foreman
14 | Compaction of bedding |  | D1.29, D2.7.7 |  | Bedding |  | M | Compacted layers not exceeding 200mm or 1/3 the pipe OD (whichever is lesser). |  |  | During construction | Monitor | Sign This ITP | Supervisor/Foreman
15 | Concrete pours |  | D1.24 |  | Sign off |  | W | Concrete pours to be inspected by Engineer's Rep prior to backfilling |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Photos/concrete dockets
16 | DN1050 Manhole F25383 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
17 | DN1050 Manhole F25384 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
18 | DN1050 Manhole F25385 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
19 | DN1050 Manhole F25386 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
20 | DN1050 Manhole F25387 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
21 | DN1050 Manhole F25389 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
22 | DN1050 Manhole F25388 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
23 | Connect into existing manhole F25215 |  | D18 |  | Inspection |  | W | Engineer's Rep to inspect connection into existing manhole |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman
24 | Encountered Services Sheet |  | Contract document Appendix X, D2.7.4.3 |  | Record |  | H | Record service on ICC encountered services sheet for services found on main and laterals |  |  | During construction | Record | Sign This ITP | Supervisor/Foreman | Complete encountered service sheet for each service
25 | Drainage Connection Sheet |  | Contract document Appendix XI |  | Record |  | H | Record detail on ICC drainage connection sheet for each lateral installed |  |  | During construction | Record | Sign This ITP | Supervisor/Foreman | Complete drainage connection sheet for each lateral installed
26 | Manhole (MH) Inspection Sheet |  | Contract document Appendix XV |  | Record |  | H | Record detail on ICC manhole inspection sheet for each manhole installed |  |  | During construction | Record | Sign This ITP | Supervisor/Foreman | Complete manhole installation sheet for each manhole installed
27 | Plateau Testing |  | D2.7.7 |  | Test |  | H | Plateau test to be undertaken at start of backfill to calibrate compaction methodology |  |  | Prior to backfill | Test | Sign This ITP | Contractor's Rep
28 | Compaction of AP65 - Clegg Tests |  | Contract document Appendix XIII, D2.7.7 |  | Record |  | W | AP65 to be compacted in layers not exceeding 200mm depth. Clegg testing to be undertaken at 6m intervals. Record results on the ICC Clegg test result sheet. |  |  | During backfill | Clegg test | Sign This ITP | Supervisor/Foreman
29 | Compaction of AP65 - Test Results to Engineer |  | D1.29, D2.7 |  | Test Point |  | W | NDM testing to be undertaken every 120m and achieve compaction of at least 95%. Results to be provided to Engineer at end of each stage. |  |  | During construction | NDM Test | Sign This ITP | Contractor's Rep | NDM test results
30 | Compaction of AP40 - Test Results to Engineer |  | D1.29, D2.7 |  | Test Point |  | W | NDM testing to be undertaken every 20m and achieve compaction of at least 98%. Results to be provided to Engineer at end of each stage. |  |  | During construction | NDM Test | Sign This ITP | Contractor's Rep | NDM test results
31 | Foul sewer main pressure testing |  | AS/NZS2566:2 |  | Test Point |  | H | Pressure test of new main, including connections to boundary |  |  | During construction | Pressure test | Sign This ITP | Supervisor/Contractor's Rep
32 | Height check and CCTV - MH F25383 - F25384 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
33 | Height check and CCTV - MH F25384 - F25385 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
34 | Height check and CCTV - MH F25385 - F25386 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
35 | Height check and CCTV - MH F25386 - F25387 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
36 | Height check and CCTV - MH F25387 - F25388 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
37 | Height check and CCTV - MH F25388 - F25389 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
38 | Height check and CCTV - MH F25389 - F25215 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
39 | Asphalt prep |  | D2.8, D12 |  | Sign off |  | H | Engineer to approve area is ready for asphalt. Prep and overcuts completed and compaction results satisfactory. |  |  | Prior to asphalt | Inspection | Sign This ITP | Engineer/Engineer's Rep
40 | Defect walkovers |  |  |  | Inspection |  | H | Contract management team to walk over site and inspect for any defects. List to be made by Engineer and provided to SR for rectification. |  |  | Post construction | Inspection | Sign This ITP | Contractor's Rep
41 | Supply of QA documentation |  | D17 |  | Sign off |  | W | Remaining QA documentation to be uploaded into Sharepoint |  |  | Post construction | Inspection | Sign This ITP | Contractor's Rep
42 | Supply of Asbuilts |  | D17 |  | Sign off |  | W | Asbuilt data, DWG format drawings and red pen mark- ups provided to Engineer |  |  | Post construction | Inspection | Sign This ITP | Contractor's Rep
INSPECTION TEST PLAN CONSTRUCTION
Foreman |  |  | Nigel Renton Kate Gentle Josh Faulkner Rob Hayes |  |  |  | Action | Morell-Nelson Foulsewer Renewal
Contractor's Representative | [7 empty] | W |  |  | Witness | Stage 2 - Nelson Street, between Tramway Road and Martin Street
Contract Manager | [7 empty] | H |  |  | Hold Point
Engineer | [7 empty] | M |  |  | Monitor | Job Number: |  | 4814 | Version:
No: | Detail |  |  |  | Inspection / Test Point |  | ACTION | Conformance Criteria (Whats Required) |  |  | Frequency | Inspection / Test Method | Verification Records | Signatory | Comments
1 | ITP sign off |  |  |  | Sign off |  | H | Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed. |  |  | Prior to commencement | Review | Sign This ITP | Divisional Manager
2 | Materials testing to be provided to Engineer for acceptance |  | SR10.103 |  | Aggregate Acceptance |  | W | Laboratory test certificates: MDD and Grading Results |  |  | Prior to commencement | Lab report | Sign This ITP | Contractor's Rep
3 | Ensure Approved Plans are on site. Safety/Environmental/Quality/TMP/Permits/Site Plans |  |  |  | Review |  | W | All plans permits produced under pre-construction available on site at all times |  |  | Prior to commencement | Review | Sign This ITP | Contractor's Rep
4 | Notice to Engineer Reviewed by Divisional Manager |  |  |  | Review |  | W | All NTE's to be reviewed |  |  | Prior to submission to Engineer | Review | Sign This ITP | Contractor's Rep
5 | Variations Reviewed by Divisional Manager |  |  |  | Review |  | W | All Variations to be reviewed |  |  | Prior to submission to Engineer | Review | Sign This ITP | Contractor's Rep
6 | Site Pre-Condition Inspection |  | D1.5, D1.32.4 |  | Review |  | W | Record existing condition of site via walk-over/drive-over |  |  | Prior to excavation | Video | Sign This ITP | Contractor's Rep
7 | Powernet and Chorus locates completed |  | D1.8 |  | Inspection |  | H | All known services have been located, reference back to plans to ensure everything has been located |  |  | Prior to excavation | Inspection | Sign This ITP | Supervisor/Foreman
8 | Material inspection |  | D2, D2.4.1 |  | Material Inspection |  | W | Complete inspection of materials as they arrive to site |  |  | Upon pipe delivery | Inspection | Sign This ITP | Supervisor/Foreman
9 | Sewerage continuity |  | C1.13, D2.7.5 |  | Monitoring |  | W | Ensure there is continuity in sewerage network during construction works |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman
10 | Existing alignment markout |  | D2.7.1, C1.14 |  | Inspection/Test Point |  | H | Markout existing aligment and trench edges onsite, to be confirmed by the Engineer's Rep |  |  | Prior to commencement | Inspection | Sign This ITP | Supervisor/Foreman
11 | Inspect subgrade |  | D13.4.3, D13.4.4 |  | Inspection/Scala |  | M | Inspect subgrade as expose, complete scala if required. Contact manager for further instruction if subgrade is deemed unsuitable |  |  | During construction | Inspection/Scala | Sign This ITP | Supervisor/Foreman
12 | Pipe laying |  | D2, D2.7, D2.11.2 |  | Pipe laying |  | M | Pipe to be laid as per specification, contract document and plans |  |  | During construction | Spot checks | Sign This ITP | Supervisor/Foreman
13 | Saddles onto main, for laterals |  | D4 |  | Sign off |  | W | Install as per construction plans |  |  | During construction | Photos | Sign This ITP | Supervisor/Foreman
14 | Compaction of bedding |  | D1.29, D2.7.7 |  | Bedding |  | M | Compacted layers not exceeding 200mm or 1/3 the pipe OD (whichever is lesser). |  |  | During construction | Monitor | Sign This ITP | Supervisor/Foreman
15 | Concrete pours |  | D1.24 |  | Sign off |  | W | Concrete pours to be inspected by Engineer's Rep prior to backfilling |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Photos/concrete dockets
16 | DN1050 Manhole F25382 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
17 | DN1050 Manhole F25381 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
18 | DN1050 Manhole F25380 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
19 | DN1050 Manhole F25379 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
20 | DN1050 Manhole F25378 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
21 | DN1050 Manhole F25377 |  | D18 |  | Inspection |  | W | Complete manhole installation checklist |  |  | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist
22 | Encountered Services Sheet |  | Contract document Appendix X, D2.7.4.3 |  | Record |  | H | Record service on ICC encountered services sheet for services found on main and laterals |  |  | During construction | Record | Sign This ITP | Supervisor/Foreman | Complete encountered service sheet for each service
23 | Drainage Connection Sheet |  | Contract document Appendix XI |  | Record |  | H | Record detail on ICC drainage connection sheet for each lateral installed |  |  | During construction | Record | Sign This ITP | Supervisor/Foreman | Complete drainage connection sheet for each lateral installed
24 | Manhole (MH) Inspection Sheet |  | Contract document Appendix XV |  | Record |  | H | Record detail on ICC manhole inspection sheet for each manhole installed |  |  | During construction | Record | Sign This ITP | Supervisor/Foreman | Complete manhole installation sheet for each manhole installed
25 | Plateau Testing |  | D2.7.7 |  | Test |  | H | Plateau test to be undertaken at start of backfill to calibrate compaction methodology |  |  | Prior to backfill | Test | Sign This ITP | Contractor's Rep
26 | Compaction of AP65 - Clegg Tests |  | Contract document Appendix XIII, D2.7.7 |  | Record |  | W | AP65 to be compacted in layers not exceeding 200mm depth. Clegg testing to be undertaken at 6m intervals. Record results on the ICC Clegg test result sheet. |  |  | During backfill | Clegg test | Sign This ITP | Supervisor/Foreman
27 | Compaction of AP65 - Test Results to Engineer |  | D1.29, D2.7 |  | Test Point |  | W | NDM testing to be undertaken every 120m and achieve compaction of at least 95%. Results to be provided to Engineer at end of each stage. |  |  | During construction | NDM Test | Sign This ITP | Contractor's Rep | NDM test results
28 | Compaction of AP40 - Test Results to Engineer |  | D1.29, D2.7 |  | Test Point |  | W | NDM testing to be undertaken every 20m and achieve compaction of at least 98%. Results to be provided to Engineer at end of each stage. |  |  | During construction | NDM Test | Sign This ITP | Contractor's Rep | NDM test results
29 | Foul sewer main pressure testing |  | AS/NZS2566:2 |  | Test Point |  | H | Pressure test of new main, including connections to boundary |  |  | During construction | Pressure test | Sign This ITP | Supervisor/Contractor's Rep
30 | Height check and CCTV - MH F25382 - F25381 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
31 | Height check and CCTV - MH F25381 - F25380 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
32 | Height check and CCTV - MH F25380 - F25379 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
33 | Height check and CCTV - MH F25379 - F25378 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
34 | Height check and CCTV - MH F25378 - F25377 |  | D2.9.3 |  | Sign off |  | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. |  |  | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage
35 | Asphalt prep |  | D2.8, D12 |  | Sign off |  | H | Engineer to approve area is ready for asphalt. Prep and overcuts completed and compaction results satisfactory. |  |  | Prior to asphalt | Inspection | Sign This ITP | Engineer/Engineer's Rep
36 | Defect walkovers |  |  |  | Inspection |  | H | Contract management team to walk over site and inspect for any defects. List to be made by Engineer and provided to SR for rectification. |  |  | Post construction | Inspection | Sign This ITP | Contractor's Rep
37 | Supply of QA documentation |  | D17 |  | Sign off |  | W | Remaining QA documentation to be uploaded into Sharepoint |  |  | Post construction | Inspection | Sign This ITP | Contractor's Rep
38 | Supply of Asbuilts |  | D17 |  | Sign off |  | W | Asbuilt data, DWG format drawings and red pen mark- ups provided to Engineer |  |  | Post construction | Inspection | Sign This ITP | Contractor's Rep
Manhole Installation Checklist
Contract Name: | [9 empty] | Contract No:
Location:
Date:
Installation Checklist
Base Installation |  | Yes |  | No |  | N/A | Comments
Check plans i.e. height and location
Location of services has been completed
Cut existing surface to suit
Excavate to design depth
Check lifting chains tag
Place and compact bedding
Place base
Cut holes for pipe connections
Install pipes into manhole
check 1m flexible joint
2 pot pipe joins
Pour Corbels and haunch
Riser Installlation |  | Yes |  | No |  | N/A | Comments
Install Sealant between risers
Place riser
Repeat as needed
Steps - If required
Lid Instillation |  | Yes |  | No |  | N/A | Comments
Install sealant
Place concrete lid
Install Cast iron lid
Check lid level
Concrete lid
Backfill |  | Yes |  | No |  | N/A | Comments
Bed manhole and pipes
Compact in 250mm layers to clegg 35
Finish level to be at 98% NDM
|  | Name |  |  |  |  | Signed |  | Date
Completed By
Date JO \ 0S \1
"! •