## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Construction - Stage 1 - Morell Street, Nelson Street between Hardy Street and Martin Street | itp
section | Details
checkpoint | 1 - ITP sign off
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed.
label | Frequency - Prior to commencement
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Divisional Manager
holdpoint | HOLD POINT
checkpoint | 2 - Materials testing to be provided to Engineer for acceptance
label | SR10.103
label | Inspection / Test Point - Aggregate Acceptance
label | ACTION - W
label | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
label | Frequency - Prior to commencement
label | Inspection / Test Method - Lab report
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 3 - Ensure Approved Plans are on site. Safety/Environmental/Quality/TMP/Permits/Site Plans
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All plans permits produced under pre-construction available on site at all times
label | Frequency - Prior to commencement
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 4 - Notice to Engineer Reviewed by Contract Manager
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All NTE's to be reviewed
label | Frequency - Prior to submission to Engineer
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 5 - Variations Reviewed by Contract Manager
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All Variations to be reviewed
label | Frequency - Prior to submission to Engineer
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 6 - Site Pre-Condition Inspection
label | D1.5, D1.32.4
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - Record existing condition of site via walk-over/drive-over
label | Frequency - Prior to excavation
label | Inspection / Test Method - Video
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 7 - Powernet and Chorus locates completed
label | D1.8
label | Inspection / Test Point - Inspection
label | ACTION - H
label | Conformance Criteria (Whats Required) - All known services have been located, reference back to plans to ensure everything has been located
label | Frequency - Prior to excavation
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
holdpoint | HOLD POINT
checkpoint | 8 - Material inspection
label | D2, D2.4.1
label | Inspection / Test Point - Material Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete inspection of materials as they arrive to site
label | Frequency - Upon pipe delivery
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 9 - Sewerage continuity
label | C1.13, D2.7.5
label | Inspection / Test Point - Monitoring
label | ACTION - W
label | Conformance Criteria (Whats Required) - Ensure there is continuity in sewerage network during construction works
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 10 - Existing alignment markout
label | D2.7.1, C1.14
label | Inspection / Test Point - Inspection/Test Point
label | ACTION - H
label | Conformance Criteria (Whats Required) - Markout existing aligment and trench edges onsite, to be confirmed by the Engineer's Rep
label | Frequency - Prior to commencement
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
holdpoint | HOLD POINT
checkpoint | 11 - Inspect subgrade
label | D13.4.3, D13.4.4
label | Inspection / Test Point - Inspection/Scala
label | ACTION - M
label | Conformance Criteria (Whats Required) - Inspect subgrade as expose, complete scala if required. Contact manager for further instruction if subgrade is deemed unsuitable
label | Frequency - During construction
label | Inspection / Test Method - Inspection/Scala
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 12 - Pipe laying
label | D2, D2.7, D2.11.2
label | Inspection / Test Point - Pipe laying
label | ACTION - M
label | Conformance Criteria (Whats Required) - Pipe to be laid as per specification, contract document and plans
label | Frequency - During construction
label | Inspection / Test Method - Spot checks
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 13 - Saddles onto main, for laterals
label | D4
label | Inspection / Test Point - Sign off
label | ACTION - W
label | Conformance Criteria (Whats Required) - Install as per construction plans
label | Frequency - During construction
label | Inspection / Test Method - Photos
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 14 - Compaction of bedding
label | D1.29, D2.7.7
label | Inspection / Test Point - Bedding
label | ACTION - M
label | Conformance Criteria (Whats Required) - Compacted layers not exceeding 200mm or 1/3 the pipe OD (whichever is lesser).
label | Frequency - During construction
label | Inspection / Test Method - Monitor
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 15 - Concrete pours
label | D1.24
label | Inspection / Test Point - Sign off
label | ACTION - W
label | Conformance Criteria (Whats Required) - Concrete pours to be inspected by Engineer's Rep prior to backfilling
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Photos/concrete dockets
checkpoint | 16 - DN1050 Manhole F25383
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 17 - DN1050 Manhole F25384
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 18 - DN1050 Manhole F25385
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 19 - DN1050 Manhole F25386
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 20 - DN1050 Manhole F25387
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 21 - DN1050 Manhole F25389
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 22 - DN1050 Manhole F25388
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 23 - Connect into existing manhole F25215
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Engineer's Rep to inspect connection into existing manhole
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 24 - Encountered Services Sheet
label | Contract document Appendix X, D2.7.4.3
label | Inspection / Test Point - Record
label | ACTION - H
label | Conformance Criteria (Whats Required) - Record service on ICC encountered services sheet for services found on main and laterals
label | Frequency - During construction
label | Inspection / Test Method - Record
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete encountered service sheet for each service
holdpoint | HOLD POINT
checkpoint | 25 - Drainage Connection Sheet
label | Contract document Appendix XI
label | Inspection / Test Point - Record
label | ACTION - H
label | Conformance Criteria (Whats Required) - Record detail on ICC drainage connection sheet for each lateral installed
label | Frequency - During construction
label | Inspection / Test Method - Record
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete drainage connection sheet for each lateral installed
holdpoint | HOLD POINT
checkpoint | 26 - Manhole (MH) Inspection Sheet
label | Contract document Appendix XV
label | Inspection / Test Point - Record
label | ACTION - H
label | Conformance Criteria (Whats Required) - Record detail on ICC manhole inspection sheet for each manhole installed
label | Frequency - During construction
label | Inspection / Test Method - Record
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete manhole installation sheet for each manhole installed
holdpoint | HOLD POINT
checkpoint | 27 - Plateau Testing
label | D2.7.7
label | Inspection / Test Point - Test
label | ACTION - H
label | Conformance Criteria (Whats Required) - Plateau test to be undertaken at start of backfill to calibrate compaction methodology
label | Frequency - Prior to backfill
label | Inspection / Test Method - Test
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
holdpoint | HOLD POINT
checkpoint | 28 - Compaction of AP65 - Clegg Tests
label | Contract document Appendix XIII, D2.7.7
label | Inspection / Test Point - Record
label | ACTION - W
label | Conformance Criteria (Whats Required) - AP65 to be compacted in layers not exceeding 200mm depth. Clegg testing to be undertaken at 6m intervals. Record results on the ICC Clegg test result sheet.
label | Frequency - During backfill
label | Inspection / Test Method - Clegg test
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 29 - Compaction of AP65 - Test Results to Engineer
label | D1.29, D2.7
label | Inspection / Test Point - Test Point
label | ACTION - W
label | Conformance Criteria (Whats Required) - NDM testing to be undertaken every 120m and achieve compaction of at least 95%. Results to be provided to Engineer at end of each stage.
label | Frequency - During construction
label | Inspection / Test Method - NDM Test
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
label | Comments - NDM test results
checkpoint | 30 - Compaction of AP40 - Test Results to Engineer
label | D1.29, D2.7
label | Inspection / Test Point - Test Point
label | ACTION - W
label | Conformance Criteria (Whats Required) - NDM testing to be undertaken every 20m and achieve compaction of at least 98%. Results to be provided to Engineer at end of each stage.
label | Frequency - During construction
label | Inspection / Test Method - NDM Test
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
label | Comments - NDM test results
checkpoint | 31 - Foul sewer main pressure testing
label | AS/NZS2566:2
label | Inspection / Test Point - Test Point
label | ACTION - H
label | Conformance Criteria (Whats Required) - Pressure test of new main, including connections to boundary
label | Frequency - During construction
label | Inspection / Test Method - Pressure test
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
holdpoint | HOLD POINT
checkpoint | 32 - Height check and CCTV - MH F25383 - F25384
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 33 - Height check and CCTV - MH F25384 - F25385
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 34 - Height check and CCTV - MH F25385 - F25386
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 35 - Height check and CCTV - MH F25386 - F25387
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 36 - Height check and CCTV - MH F25387 - F25388
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 37 - Height check and CCTV - MH F25388 - F25389
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 38 - Height check and CCTV - MH F25389 - F25215
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 39 - Asphalt prep
label | D2.8, D12
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Engineer to approve area is ready for asphalt. Prep and overcuts completed and compaction results satisfactory.
label | Frequency - Prior to asphalt
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Engineer/Engineer's Rep
holdpoint | HOLD POINT
checkpoint | 40 - Defect walkovers
label | Inspection / Test Point - Inspection
label | ACTION - H
label | Conformance Criteria (Whats Required) - Contract management team to walk over site and inspect for any defects. List to be made by Engineer and provided to SR for rectification.
label | Frequency - Post construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
holdpoint | HOLD POINT
checkpoint | 41 - Supply of QA documentation
label | D17
label | Inspection / Test Point - Sign off
label | ACTION - W
label | Conformance Criteria (Whats Required) - Remaining QA documentation to be uploaded into Sharepoint
label | Frequency - Post construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 42 - Supply of Asbuilts
label | D17
label | Inspection / Test Point - Sign off
label | ACTION - W
label | Conformance Criteria (Whats Required) - Asbuilt data, DWG format drawings and red pen mark- ups provided to Engineer
label | Frequency - Post construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checklist | ITP - Construction - Stage 2 - Nelson Street, between Tramway Road and Martin Street | itp
section | Details
checkpoint | 1 - ITP sign off
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed.
label | Frequency - Prior to commencement
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Divisional Manager
holdpoint | HOLD POINT
checkpoint | 2 - Materials testing to be provided to Engineer for acceptance
label | SR10.103
label | Inspection / Test Point - Aggregate Acceptance
label | ACTION - W
label | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
label | Frequency - Prior to commencement
label | Inspection / Test Method - Lab report
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 3 - Ensure Approved Plans are on site. Safety/Environmental/Quality/TMP/Permits/Site Plans
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All plans permits produced under pre-construction available on site at all times
label | Frequency - Prior to commencement
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 4 - Notice to Engineer Reviewed by Divisional Manager
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All NTE's to be reviewed
label | Frequency - Prior to submission to Engineer
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 5 - Variations Reviewed by Divisional Manager
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - All Variations to be reviewed
label | Frequency - Prior to submission to Engineer
label | Inspection / Test Method - Review
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 6 - Site Pre-Condition Inspection
label | D1.5, D1.32.4
label | Inspection / Test Point - Review
label | ACTION - W
label | Conformance Criteria (Whats Required) - Record existing condition of site via walk-over/drive-over
label | Frequency - Prior to excavation
label | Inspection / Test Method - Video
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 7 - Powernet and Chorus locates completed
label | D1.8
label | Inspection / Test Point - Inspection
label | ACTION - H
label | Conformance Criteria (Whats Required) - All known services have been located, reference back to plans to ensure everything has been located
label | Frequency - Prior to excavation
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
holdpoint | HOLD POINT
checkpoint | 8 - Material inspection
label | D2, D2.4.1
label | Inspection / Test Point - Material Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete inspection of materials as they arrive to site
label | Frequency - Upon pipe delivery
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 9 - Sewerage continuity
label | C1.13, D2.7.5
label | Inspection / Test Point - Monitoring
label | ACTION - W
label | Conformance Criteria (Whats Required) - Ensure there is continuity in sewerage network during construction works
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 10 - Existing alignment markout
label | D2.7.1, C1.14
label | Inspection / Test Point - Inspection/Test Point
label | ACTION - H
label | Conformance Criteria (Whats Required) - Markout existing aligment and trench edges onsite, to be confirmed by the Engineer's Rep
label | Frequency - Prior to commencement
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
holdpoint | HOLD POINT
checkpoint | 11 - Inspect subgrade
label | D13.4.3, D13.4.4
label | Inspection / Test Point - Inspection/Scala
label | ACTION - M
label | Conformance Criteria (Whats Required) - Inspect subgrade as expose, complete scala if required. Contact manager for further instruction if subgrade is deemed unsuitable
label | Frequency - During construction
label | Inspection / Test Method - Inspection/Scala
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 12 - Pipe laying
label | D2, D2.7, D2.11.2
label | Inspection / Test Point - Pipe laying
label | ACTION - M
label | Conformance Criteria (Whats Required) - Pipe to be laid as per specification, contract document and plans
label | Frequency - During construction
label | Inspection / Test Method - Spot checks
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 13 - Saddles onto main, for laterals
label | D4
label | Inspection / Test Point - Sign off
label | ACTION - W
label | Conformance Criteria (Whats Required) - Install as per construction plans
label | Frequency - During construction
label | Inspection / Test Method - Photos
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 14 - Compaction of bedding
label | D1.29, D2.7.7
label | Inspection / Test Point - Bedding
label | ACTION - M
label | Conformance Criteria (Whats Required) - Compacted layers not exceeding 200mm or 1/3 the pipe OD (whichever is lesser).
label | Frequency - During construction
label | Inspection / Test Method - Monitor
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 15 - Concrete pours
label | D1.24
label | Inspection / Test Point - Sign off
label | ACTION - W
label | Conformance Criteria (Whats Required) - Concrete pours to be inspected by Engineer's Rep prior to backfilling
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Photos/concrete dockets
checkpoint | 16 - DN1050 Manhole F25382
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 17 - DN1050 Manhole F25381
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 18 - DN1050 Manhole F25380
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 19 - DN1050 Manhole F25379
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 20 - DN1050 Manhole F25378
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 21 - DN1050 Manhole F25377
label | D18
label | Inspection / Test Point - Inspection
label | ACTION - W
label | Conformance Criteria (Whats Required) - Complete manhole installation checklist
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete SR manhole checklist
checkpoint | 22 - Encountered Services Sheet
label | Contract document Appendix X, D2.7.4.3
label | Inspection / Test Point - Record
label | ACTION - H
label | Conformance Criteria (Whats Required) - Record service on ICC encountered services sheet for services found on main and laterals
label | Frequency - During construction
label | Inspection / Test Method - Record
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete encountered service sheet for each service
holdpoint | HOLD POINT
checkpoint | 23 - Drainage Connection Sheet
label | Contract document Appendix XI
label | Inspection / Test Point - Record
label | ACTION - H
label | Conformance Criteria (Whats Required) - Record detail on ICC drainage connection sheet for each lateral installed
label | Frequency - During construction
label | Inspection / Test Method - Record
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete drainage connection sheet for each lateral installed
holdpoint | HOLD POINT
checkpoint | 24 - Manhole (MH) Inspection Sheet
label | Contract document Appendix XV
label | Inspection / Test Point - Record
label | ACTION - H
label | Conformance Criteria (Whats Required) - Record detail on ICC manhole inspection sheet for each manhole installed
label | Frequency - During construction
label | Inspection / Test Method - Record
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
label | Comments - Complete manhole installation sheet for each manhole installed
holdpoint | HOLD POINT
checkpoint | 25 - Plateau Testing
label | D2.7.7
label | Inspection / Test Point - Test
label | ACTION - H
label | Conformance Criteria (Whats Required) - Plateau test to be undertaken at start of backfill to calibrate compaction methodology
label | Frequency - Prior to backfill
label | Inspection / Test Method - Test
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
holdpoint | HOLD POINT
checkpoint | 26 - Compaction of AP65 - Clegg Tests
label | Contract document Appendix XIII, D2.7.7
label | Inspection / Test Point - Record
label | ACTION - W
label | Conformance Criteria (Whats Required) - AP65 to be compacted in layers not exceeding 200mm depth. Clegg testing to be undertaken at 6m intervals. Record results on the ICC Clegg test result sheet.
label | Frequency - During backfill
label | Inspection / Test Method - Clegg test
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Foreman
checkpoint | 27 - Compaction of AP65 - Test Results to Engineer
label | D1.29, D2.7
label | Inspection / Test Point - Test Point
label | ACTION - W
label | Conformance Criteria (Whats Required) - NDM testing to be undertaken every 120m and achieve compaction of at least 95%. Results to be provided to Engineer at end of each stage.
label | Frequency - During construction
label | Inspection / Test Method - NDM Test
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
label | Comments - NDM test results
checkpoint | 28 - Compaction of AP40 - Test Results to Engineer
label | D1.29, D2.7
label | Inspection / Test Point - Test Point
label | ACTION - W
label | Conformance Criteria (Whats Required) - NDM testing to be undertaken every 20m and achieve compaction of at least 98%. Results to be provided to Engineer at end of each stage.
label | Frequency - During construction
label | Inspection / Test Method - NDM Test
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
label | Comments - NDM test results
checkpoint | 29 - Foul sewer main pressure testing
label | AS/NZS2566:2
label | Inspection / Test Point - Test Point
label | ACTION - H
label | Conformance Criteria (Whats Required) - Pressure test of new main, including connections to boundary
label | Frequency - During construction
label | Inspection / Test Method - Pressure test
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
holdpoint | HOLD POINT
checkpoint | 30 - Height check and CCTV - MH F25382 - F25381
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 31 - Height check and CCTV - MH F25381 - F25380
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 32 - Height check and CCTV - MH F25380 - F25379
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 33 - Height check and CCTV - MH F25379 - F25378
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 34 - Height check and CCTV - MH F25378 - F25377
label | D2.9.3
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
label | Frequency - During construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Supervisor/Contractor's Rep
label | Comments - CCTV footage
holdpoint | HOLD POINT
checkpoint | 35 - Asphalt prep
label | D2.8, D12
label | Inspection / Test Point - Sign off
label | ACTION - H
label | Conformance Criteria (Whats Required) - Engineer to approve area is ready for asphalt. Prep and overcuts completed and compaction results satisfactory.
label | Frequency - Prior to asphalt
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Engineer/Engineer's Rep
holdpoint | HOLD POINT
checkpoint | 36 - Defect walkovers
label | Inspection / Test Point - Inspection
label | ACTION - H
label | Conformance Criteria (Whats Required) - Contract management team to walk over site and inspect for any defects. List to be made by Engineer and provided to SR for rectification.
label | Frequency - Post construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
holdpoint | HOLD POINT
checkpoint | 37 - Supply of QA documentation
label | D17
label | Inspection / Test Point - Sign off
label | ACTION - W
label | Conformance Criteria (Whats Required) - Remaining QA documentation to be uploaded into Sharepoint
label | Frequency - Post construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checkpoint | 38 - Supply of Asbuilts
label | D17
label | Inspection / Test Point - Sign off
label | ACTION - W
label | Conformance Criteria (Whats Required) - Asbuilt data, DWG format drawings and red pen mark- ups provided to Engineer
label | Frequency - Post construction
label | Inspection / Test Method - Inspection
label | Verification Records - Sign This ITP
label | Signatory - Contractor's Rep
checklist | Manhole Installation Checklist
section | Base Installation
checkpoint | Check plans i.e. height and location
checkpoint | Location of services has been completed
checkpoint | Cut existing surface to suit
checkpoint | Excavate to design depth
checkpoint | Check lifting chains tag
checkpoint | Place and compact bedding
checkpoint | Place base
checkpoint | Cut holes for pipe connections
checkpoint | Install pipes into manhole
checkpoint | Check 1m flexible joint
checkpoint | 2 pot pipe joins
checkpoint | Pour Corbels and haunch
section | Riser Installation
checkpoint | Install Sealant between risers
checkpoint | Place riser
checkpoint | Repeat as needed
checkpoint | Steps - If required
section | Lid Instillation
checkpoint | Install sealant
checkpoint | Place concrete lid
checkpoint | Install Cast iron lid
checkpoint | Check lid level
checkpoint | Concrete lid
section | Backfill
checkpoint | Bed manhole and pipes
checkpoint | Compact in 250mm layers to clegg 35
checkpoint | Finish level to be at 98% NDM
checkpoint | Completed By
textbox | Name
date | Date
holdpoint | Signed