## Sheet1
ConQA Team Notes:
Document Title: |  | ITP-286-CIV-PSSD-Tactile Installation
ITP Description: |  | PSSD-Tactile Installation
Discipline (e.g. CIV/STR/RAIL: |  | 286-CIV
Revision Number: |  | 0
Revision Date: |  | 2025-06-16
ITP created by: |  | Laclan Shoemaker
ITP approved for use by: |  | Romualdo Magpantay
Special Notes to ConQA Team : |  | ITP for PSSD
Inspection & Test Plan - Tactile Installation
[9 empty] | Revision: | 0
[9 empty] | Date: | 2025-06-16
Legend: HP: Hold Point, HP* Internal Hold Point, WP: Witness Point, IP: Inspection Point, SP: Surveillance Point
Item | Task/Activity Description | Reference | Acceptance Criteria | Inspection / Test |  |  | Responsibility | Verifying Documents | Date Completed | Sign-off
|  |  |  | Method | Frequency | Category
1 | Referenced Documentation
1.1 | Non Dependent | AS1428.4.1 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.2 | Non Dependent | VicRoads Section 160.A9 | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
1.3 | Non Dependent | IFC Drawings | N/A | N/A | N/A | N/A | N/A | N/A | NA | N/A
2 | Preliminaries - Materials
2.1 | Material Conformance | AS1428.4.1 Section 2.2 & 2.3.1 | Tactile Indicators must conform with the requirements of AS1428.1.1 Section 2.2 & 2.3.1 Attach: TeamBinder Material Approval Ref No | Document Review | Prior to works start | HP | Nominated Authority | Conqa HP Release
3 | Preliminaries - Documentations
3.1 | Documentation Conformance | DoT Handover Process | Tactile to be black in colour, VicRoads approved as per design note RDN 06-05 and DDA Compliant | Visual & Document Review | Prior to works start | HP* | SE/PE | This ITP Signed-off
4 | Pre-construction / Pre-installation Activities
4.1 | Survey Set-out | IFC Drawings | The required positions of the tactiles are clearly set out by a surveyor as per IFC Drawings. | Measure Visual | Per Lot | IP | Surveyor SE/PE/Site Supervisor | This ITP Signed-off
5 | Construction / Installation Activities
5.1 | Installation | AS1428.4.1 Section 2.3.3 | Notify Nominated Authority prior to installation. Warning indicators shall be installed as follows: (a) For the full width of the path of travel (b) Perpendicular to the direction of travel when approaching the hazard. (c) Set back 300 +/-10 mm from the edge of the hazard except at railway platforms and wharves. (d) Where integrated warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below, over a minimum depth of 600 mm to 800 mm from the direction of approach. (e) Where discrete warning TGSIs are used over a depth of 300 mm to 400 mm, the arrangement shall be as shown in Figure 2.1 below with a minimum of 6 discrete truncated cones in the direction of travel. (f) Where discrete warning TGSIs need to be detected by a person approaching at an angle to the continuous accessible path of travel, the TGSIs shall be arranged as shown in Figure 2.1 below with a minimum of 12 discrete truncated cones in the direction of travel. Where required on a path of travel, warning indicators shall be located at both the top and bottom of stairways, ramps, escalators and moving walks | Visual/Site Inspection & Document Review | Per Lot | HP | Nominated Authority | Conqa HP Release
5.2 | Laboratory and On-site measurement of luminance contrast | AS1428.4.1 Appendix E | Submit Test report to AS1428.4.1 E5.4: The following shall be reported: (a) Full description of the surfaces tested with product details where known. (b) The instrument being a luminance meter with a 1° measurement area corrected to approximate the CIE 1931 Standard Observer. (c) The location of the sample, if on-site. (d) The location of the sample of the measurements on the TGSI. (e) A description of the light source(s) illuminating the sample, including type, [e.g. fluorescent tube, incandescent, high pressure sodium discharge, metal halide, and colour (in general terms)]. (f) The mean luminous reflectance of the adjacent surrounds to the tactile indicator under the conditions set out in Paragraph E5.3 (g) The mean luminous reflectance of the tactile indicator under the conditions set out in Paragraph E5.3 (h) The luminance contrast with the surrounds on both sides of the tactile indicator. (i) A reference to this test method, i.e., AS/NZS 1428.4, Paragraph E5, Appendix E. Attach: Laboratory Test report | Visual/Site Inspection & Document Review | Per Lot | IP | SE/PE | This ITP Signed-off
5.3 | Distance between tactiles and sleeve | DoT Handover Process | Distance between tactile and sleeve to be a minimum of 300mm as per note 1 of the Handover Process | Visual Inspection Measure | Per Lot | HP* | SE/PE | This ITP Signed-off
6 | Post-construction / Post-installation Activities
6.1 | As-built Survey | IFC Drawings VR 160.A9 | As-constructed’ information shall be progressively documented during the work under the Contract and shall be provided to the Superintendent in a neat and clean format Attach: Survey As-built / Survey Report Attach: Survey Conformance Data/Report | Document Review | Per Lot | IP | Nominated Authority | This ITP Signed-off
6.2 | Non-conformance Report (NCR) Closure | MRPA Quality Management Plan | Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed. | Document Review | Once, prior to closure of this lot / element / Work area | HP* | SE/PE/SPE | This ITP Signed-off
Final Inspection
On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
Print Name: Position: Signature: Date: / /