## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-218-CIV-HOP-Type A Fill - Road Rev 0 | itp | ITP-218-CIV-HOP-Type A Fill - Road |  | 95ca80eb-6742-4732-be0f-14ef2be1da06
| section | 1. Referenced Documentation
| checkpoint-no-value | Referenced Documentation
19ddd7c6-d115-5078-bbfa-2bb725553b10 | note | Document Title: ITP-218-CIV-HOP- Type A Fill - Road (Supply and Install)
b1688898-af57-5a77-b796-be05817a05af | note | ITP Description: Type A Fill - Road (Supply and Install)
db066cac-7e2c-5d19-b91a-f877289f6ec8 | note | Discipline (e.g. CIV/STR/RAIL): 218-CIV-HOP-
aa07528d-c2cf-5845-a820-98924efb0a11 | note | Revision Number: 0
0ec61fc5-4ab9-5a33-974d-2c3a97579163 | note | Revision Date: 28/10/2024
42c6c8bc-a728-529d-bdef-fc6d9a3acc70 | note | ITP created by: Cedric Guico
04ad805a-eff2-5531-9e82-cc0055cf958c | note | ITP approved for use by: Pradeep Tisala
281098cd-0d92-5d3d-a48c-817a97cbe6d8 | note | 1.1 - Non Dependent
0d370d08-5c61-5283-bda0-053a995f43b1 | note | Reference - IFC Drawings
a175d07e-8fa3-58a7-804b-2f046966f1fe | note | VicRoads Standard Section 176 (Sept 2008)
89f57077-9de4-5911-a3e1-1a1d91bcb083 | note | VicRoads Section
edf8ac37-d178-5d13-8755-adec757a13ad | note | 204 (Dec 2015)
2c2d41dc-feda-59d7-b60f-704c2c9a0003 | note | Code of Practice RC500.20
662bbf3d-951b-50b5-b8bd-a70bca4fca17 | note | Code of Practice RC500.5
| section | 2. Preliminaries-Materials
| checkpoint | 2.1 - Material Conformance
98ea6876-c08b-583d-8ece-2f3a26d7f0f4 | note | Reference - Section 204.04 b) Table 204.041 IFC Drawings
83e29795-c43f-50fc-8fa2-543f0d35518e | note | Acceptance Criteria - Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
167ab4eb-6f88-581a-9620-bc5b281df4a4 | note | ○ Assigned CBR≥8%
33a5a072-9fa8-5fe9-a56e-5267cc9e3d29 | note | ○ Swell ≤ 1.5%
11eff2b1-91c3-5168-82ed-dead1c7189d9 | note | ○ Permeability ≤ 5X10-9 m/s
36306193-dca1-5c67-8fc4-1d99ff482761 | note | ○ Grading:
f55471f2-e841-5a00-83d0-23e001f388d9 | note | • 75.0mm 100%
887823ec-9b7b-582a-af22-8457a6ebb6b2 | note | • 4.75mm 40-80%
dc54b8b5-b459-5f62-a21d-08d80d24615a | note | • 0.075mm 10-40%
b7ae7f43-83a6-5d51-84bc-31cae86c85ee | textbox | Reference: Material approval in Teambinder:
c8a617a6-88fb-51f7-a264-6db870f23887 | note | Method - Document Review
bde6dbec-3059-5cf3-a637-a43460fe1ee2 | note | Frequency - Once, for each material type
39605636-0715-590b-bb5a-380592c78d51 | note | Category - HP
eeaa1b45-2897-5e95-85ba-dfc5f7aeace6 | note | Responsibility - SE/Nominated Authority
ced1e042-174c-5234-b604-94bfc7759ea5 | note | Verifying Documents - Supplier Material Conformance Certificate
c7aaa1c3-096e-5da9-915c-1ecd5398dd63 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 3. Preliminaries-Documentations
| checkpoint | 3.1 - Pre-Commencement of Fill Works
b0759753-5457-5bed-87e9-09c67cbedc64 | note | Reference - Section 204.10 (b)
dde01fa7-0e77-55d8-b99e-8a008e2f6db0 | note | Acceptance Criteria - Areas upon which fills are to be constructed shall be prepared for test rolling by the Contractor.
a936a6e6-0367-51e5-998a-7370418933a9 | note | ○ The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Nominated Authority.
8c128ebf-74b9-5107-82ef-6b8a406ca0f6 | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Nominated Authority
eaacfaaf-7b7d-5747-b321-ac7f7436a2f1 | textbox | Reference: Subgrade Preparation Lot Number:
d928f46a-4eb9-5dd7-84e8-72d8922f21ad | note | Method - Visual Inspection
52450297-61b5-529c-b685-228fd6d838cb | note | Frequency - Prior to commencement of fill works
448b9ac8-2128-5cac-9abb-4c080d4a9c13 | note | Category - HP
59978814-c441-5c3f-82a4-80f5f9427e2e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4. Pre-construction / Pre-installation Activities
| checkpoint | 4.1 - Survey Set Out
beee4df8-2fa2-5010-8c94-0a858442a29c | note | Reference - Design Drawings
3f3355ec-ca67-548b-a1e8-66251e43ddc4 | note | Acceptance Criteria - Set out pegs in place and clearly mark out limits of works.
71810a6e-d50a-5bb6-9b5c-21e263917e78 | note | ○ ATTACH: LOT MARKED UP LOCATION ON THE IFC DRAWING (LOT MAP)
c440cb81-3bad-545f-ac27-4216d29c41be | note | Method - Visual Inspection
0792c1e2-ecb0-59c1-9325-b11041ecc5c0 | note | Frequency - Each lot prior to commencement
effeed58-588f-5223-b52c-155cf0068824 | note | Category - HP*
c70536f9-703c-5dfe-ab44-97bb640b2487 | note | Responsibility - PE
526e0366-b7cc-524d-88d4-e29ab8c6f4d0 | note | Verifying Documents - Signed ITP, Lot Map
4223832a-5a5c-5059-a8a4-8b25bb2111ff | date | Date Completed:
| section | 5. Type A Fill/Verge Activities
| checkpoint | 5.1 - Placing of Fill
176d48f9-ea88-5285-ac41-9b2fb0aaf312 | note | Reference - Section 204.10
6d509333-16cb-5988-be1a-5b8ea5ac6958 | note | Acceptance Criteria - Type A material shall be spread and compacted in layers not exceeding a compacted thickness of 200 mm.
686a520a-ef35-5fa2-b9e2-6890a42bca8a | note | Method - Visual
1bc64947-7032-5632-9cf3-f9da9ace315c | note | Frequency - Each Lot
8536581c-4ebb-5f4b-976f-552301b31cfd | note | Category - WP
532cb39f-5f6c-5394-a1fe-05f08181fd15 | note | Responsibility - SE/Site Supervisor
028f99ef-7438-5c17-812d-cc0d453d025c | note | Verifying Documents - Sign ITP
9632e991-8707-5fe5-a89b-41174f8c2691 | date | Date Completed:
| checkpoint | 5.2 - Test Roll
bc1053f6-426d-5c8d-8290-4b50bbd6dece | note | Reference - Section 173.03, Section 204.12
af5ec64c-49a9-545b-85ea-f0cdfff173e3 | note | Acceptance Criteria - Each Layer shall be test rolled in accordance with Section 173. Where site access is restricted, verify with a pickaxe drop or similar, at the Nominated Authorities discretion.
61ec8b8c-24c1-53c2-976e-b1fd6879cf3c | note | Method - Test Roll as per 173.03
977373dc-abd1-55ef-b7d9-e1f6473f1220 | note | Frequency - Each Lot/Layer
b92f1bce-fc32-532f-a6d8-7835527a3a15 | note | Category - HP
8c489676-8ad4-5de8-a797-2ea97a52c6a6 | note | Responsibility - SE/Nominated Authority
1445eed7-8625-5c59-8a47-247e3ce88c05 | note | Verifying Documents - Sign ITP
279893bf-0b4c-56e3-a04b-0678c6f920ce | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 5.3 - Compaction Testing
f55954ee-9b68-51e5-ab34-9b1458a8bdb1 | note | Reference - Table 204.131 Section 204.14 c) Table 204.142
fff29af4-01d7-5c21-b947-5ca4a2198cd4 | note | Acceptance Criteria - Testing as per 204. Ensure testing is tracked and reports available.
568bb44c-b921-5c72-b677-3a2ccad7116a | note | ○ Standard Compactive Effort
b0d965cf-1d77-55f3-bf1a-4ba369586d48 | note | • For work to be tested for compliance with Scale A or Scale B compaction requirements, the number of tests per test lot shall be six.
61d17ef5-997a-583d-a3fb-15ea772fd1a7 | note | • For work to be tested for compliance with Scale C compaction requirements, the number of tests per test lot shall be three.
9092cde4-7c61-5273-b092-02aaa3a0ccae | note | ○ Compaction and Moisture content
1338cb97-fcf0-559c-a9ae-9774e3d47ba4 | note | • Scale B: Standard Compaction 98%.
3885d04c-2320-5e01-847e-f68c4e166c74 | note | ○ Lot size - the leser of one day's production or 5,000sqm
d19af8c8-4be0-55ba-bc81-856387b325af | note | ○ ATTACH: COMPACTION TEST RESULTS
9ee842e8-205d-51a0-8bd3-f9ba2164bf8a | note | Method - Review Document
93d24f45-1a3c-5321-bd94-70d63d6b3c5b | note | Frequency - Test the first 3 lots. Reduced min. frequency every 2nd lot of like material and work
85cb33c8-e079-5bde-9719-608a3171e1c2 | note | Category - IP
2ecc3657-1ed7-5673-a21a-80f8e44b9091 | note | Responsibility - SE/Site Supervisor
f47ad164-f945-521f-aab7-f41d5d05b127 | note | Verifying Documents - Sign ITP, Attach Compaction Test Report
0c9a7bca-5f38-5805-ba55-1549ea615ad1 | date | Date Completed:
| checkpoint | 5.4 - Preparation of final surface
f9b82bb1-f074-5643-b29b-7fb2364aa437 | note | Reference - Section 204.15, 204.03 (g)
b358599d-4516-5ad7-be80-ad9b0ed7cf11 | note | Acceptance Criteria - The top of the Type A material, Cut Floor Level and subgrade surfaces shall be prepared to level and shape within the tolerances specified in Clause 204.03 (g) to produce a smooth, hard, tightly bound surface, free from depressions capable of holding water).
2e81b214-320d-5be2-a437-beb9fa9dab79 | note | Method - Measure
464b1be7-6790-5494-983f-8b67a2153d73 | note | Frequency - Top layer
77d58644-c6d2-57ce-9ba8-5c0aff6d65d4 | note | Category - IP
e95038ba-0d25-52c6-aaa2-888de819955a | note | Verifying Documents - Signed ITP
567e4447-2db0-5553-a73e-6191bb507418 | date | Date Completed:
| section | Post-construction Activities
| checkpoint | 6.1 - Post Compaction Material Property Testing
1fe498ea-36f3-5781-b199-a4ec421dac81 | note | Reference - Table 204,041, Table 204.141 Section 204.14 a) or b)
a2acf588-c08e-5abc-9f7e-faaf2e9d273a | note | Acceptance Criteria - Material Properties (Not Applicable for Scale C):
09c6a4b4-4893-5c3e-9285-b68ecc83e637 | note | ○ CBR ≥ 3% and Swell ≤ 1.5%
b673a2fd-b306-51b1-889b-d317eacc20b0 | note | ○ Max Permeability = 5X10-9 m/s
0f21ac78-1ae1-5a5f-b7cf-c9d35723c602 | note | ○ Grading:
d5700551-9cab-5fa9-9eea-8813469c1113 | note | • 75.0mm 100%
235390b3-1f01-5fb6-88e5-24acf53f29fc | note | • 4.75mm 40-80%
7d9fb7eb-366d-58aa-9e38-fec02b06fd30 | note | • 0.075mm 10-40%
5f964964-92bb-5dab-843c-b5f6840189af | note | ○ Max. PI x%Passing 0.425mm = 1000 , PI = 6 to 25
6ae0dfed-7d5a-57c4-8cd2-e37a0762035f | note | ○ Scale B:
552fa734-8c62-533a-9364-22cf8497eef2 | note | • 1 Lot Test to determine: Assigned CBR and swell, Grading & Max. Particle Dimension, PI and PIx%Passing 0.425mm and permeability.
35e5575f-278a-5c7f-8976-73c3fb9f4bdd | note | • Where the first lot passes, no further testing required except where changes to the physical properties of the material are observed.
e502188e-5278-5a56-b0fa-cd05a911f591 | note | ○ Attach: Post compaction test results:
09f67c26-7277-58c2-b274-fa8b9337e463 | note | Method - Review Document
16554a5c-22a3-53e1-96b4-571e03643ee8 | note | Frequency - Refer to Section 204
aa60cf95-d546-5a8f-b229-9f9fd932ca31 | note | Category - IP
ae5efe1c-099d-5e42-9148-447d879d7d68 | note | Responsibility - SE/Site Supervisor
d8f877a5-256e-5d3f-9d98-022220ecbf8b | note | Verifying Documents - Sign ITP, Attach Material Property Test Report
fc6ff704-9b66-56f9-8c72-5bb8d40251b3 | date | Date Completed:
| checkpoint | 6.2 - Survey Conformance
1afcdb11-46a7-53b4-b422-7367c8f6676b | note | Reference - VicRoads 204.03f,g and h
14aea2ec-99ed-5b5c-b2ee-d0338c4af5bc | note | Acceptance Criteria - The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
c5fd2474-9e35-5ece-8c11-277ce44f413b | note | ○ Level tolerances Scale A:
1a1c5c16-422a-541a-9d8b-a668067c87e0 | note | • Range x = +5, -15mm
84a967bd-1223-54b3-848f-9d2f7ec67ac9 | note | • Max S = 12 mm
fc067ab8-d4da-5e6f-a362-90aef524a87d | note | • 80 measurements per lot
7d689e41-5a7f-531d-ad56-5bf646d16ada | note | ○ Level tolerances Scale B:
d70e7c38-a5ef-5d46-b9a3-a55c1b1d62f2 | note | • Range x = +5, -25mm
84cb3bd8-2fca-541e-b01c-09a998eee8dd | note | • Max S = 15 mm
443bc57e-8c3f-57d1-a503-67a77f062c40 | note | • 40 measurements per lot
a122079a-1cae-5d01-986f-53718a5bf5a6 | note | ○ Level tolerances Scale C:
cb9ff527-2887-54eb-ba39-f37ce1c56b07 | note | • Where Scale C is nominated, random levelling is not required; however no point on the subgrade surface shall be more than 10 mm above or 30 mm below the specified level.
e219ff12-c3e5-5183-bcb5-a094614ef984 | note | Method - Document Review
daf26ab1-bd00-5d1e-bb2b-6c943e8a8913 | note | Frequency - Top of Type A/Verge
2d951b43-d7b6-5ec9-9cae-abc6b6be2aee | note | Category - IP
32b59760-b09d-5e74-97a8-91a15fa8f7be | note | Responsibility - Surveyor, SE/PE/SPE
75a278e1-d5c0-509d-8ce1-69c21e3b13d6 | note | Verifying Documents - This ITP, Survey Conformance Report
278aa528-603e-5796-87d8-b74eb4ef3155 | date | Date Completed:
| checkpoint | 6.3 - Non-conformance Report (NCR) Closure
15493a6b-73f9-512d-a35b-2c8d62deb02b | note | Reference - MRPA Quality Management Plan
9541c672-cf84-5fd6-ba07-db86c9d298af | note | Acceptance Criteria - Ensure that any NCRs pertaining to the lot / element / Work area that this ITP covers, have been closed in CAMs.
df5935e4-ce18-585e-9831-c777996fdb8f | note | Method - Document Review
16188793-d0a0-599d-b7c0-154e95eeb30a | note | Frequency - Once, prior to closure of this lot / element / Work area
587af470-9522-580e-8fdb-a5e539957ecb | note | Category - HP*
f49b2e9c-74a9-5695-8f7f-fc148e296239 | note | Responsibility - SE/PE/SPE
eaeea5fd-6608-5729-876c-515e586021ae | note | Verifying Documents - This ITP
d8991b21-f937-5cfb-92a9-797dd756490a | date | Date Completed:
| checkpoint | Final Inspection
4057bd54-ea3e-523f-8a1b-047ec468001b | note | On behalf of Metropolitan Roads Program Alliance, it is hereby certified that the Works represented by the item of work listed have been tested in accordance with the Project Quality Plan and conform in all respects with the requirements of the Contract.
5587b9cd-3c63-50d1-baa2-e771eb2eda22 | textbox | Name:
5d3709b2-3e36-5745-8dbc-21af2a1747e0 | textbox | Position:
2baf4aef-881a-5dce-b570-f9446c531171 | textbox | Date Completed:
| signoff | Sign ITP