## Sheet1
1 | ITP sign off |  | Sign off | H | Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed. | Prior to commencement | Review | Sign This ITP | Divisional Manager |  | 1 - ITP sign off | 0 | Inspection / Test Point - Sign off | ACTION - H | Conformance Criteria (Whats Required) - Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed. | Frequency - Prior to commencement | Inspection / Test Method - Review | Verification Records - Sign This ITP | Signatory - Divisional Manager | Comments - | 1 - ITP sign off
2 | Materials testing to be provided to Engineer for acceptance | SR10.103 | Aggregate Acceptance | W | Laboratory test certificates: MDD and Grading Results | Prior to commencement | Lab report | Sign This ITP | Contractor's Rep |  | 2 - Materials testing to be provided to Engineer for acceptance | SR10.103 | Inspection / Test Point - Aggregate Acceptance | ACTION - W | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results | Frequency - Prior to commencement | Inspection / Test Method - Lab report | Verification Records - Sign This ITP | Signatory - Contractor's Rep | Comments - | 0
3 | Ensure Approved Plans are on site. Safety/Environmental/Quality/TMP/Permits/Site Plans |  | Review | W | All plans permits produced under pre-construction available on site at all times | Prior to commencement | Review | Sign This ITP | Contractor's Rep |  | 3 - Ensure Approved Plans are on site. Safety/Environmental/Quality/TMP/Permits/Site Plans | 0 | Inspection / Test Point - Review | ACTION - W | Conformance Criteria (Whats Required) - All plans permits produced under pre-construction available on site at all times | Frequency - Prior to commencement | Inspection / Test Method - Review | Verification Records - Sign This ITP | Signatory - Contractor's Rep | Comments - | Inspection / Test Point - Sign off
4 | Notice to Engineer Reviewed by Divisional Manager |  | Review | W | All NTE's to be reviewed | Prior to submission to Engineer | Review | Sign This ITP | Contractor's Rep |  | 4 - Notice to Engineer Reviewed by Divisional Manager | 0 | Inspection / Test Point - Review | ACTION - W | Conformance Criteria (Whats Required) - All NTE's to be reviewed | Frequency - Prior to submission to Engineer | Inspection / Test Method - Review | Verification Records - Sign This ITP | Signatory - Contractor's Rep | Comments - | ACTION - H
5 | Variations Reviewed by Divisional Manager |  | Review | W | All Variations to be reviewed | Prior to submission to Engineer | Review | Sign This ITP | Contractor's Rep |  | 5 - Variations Reviewed by Divisional Manager | 0 | Inspection / Test Point - Review | ACTION - W | Conformance Criteria (Whats Required) - All Variations to be reviewed | Frequency - Prior to submission to Engineer | Inspection / Test Method - Review | Verification Records - Sign This ITP | Signatory - Contractor's Rep | Comments - | Conformance Criteria (Whats Required) - Ensure ITP has been reviewed and signed off by the DM. No work may proceed unless this has been signed.
6 | Site Pre-Condition Inspection | D1.5, D1.32.4 | Review | W | Record existing condition of site via walk-over/drive-over | Prior to excavation | Video | Sign This ITP | Contractor's Rep |  | 6 - Site Pre-Condition Inspection | D1.5, D1.32.4 | Inspection / Test Point - Review | ACTION - W | Conformance Criteria (Whats Required) - Record existing condition of site via walk-over/drive-over | Frequency - Prior to excavation | Inspection / Test Method - Video | Verification Records - Sign This ITP | Signatory - Contractor's Rep | Comments - | Frequency - Prior to commencement
7 | Powernet and Chorus locates completed | D1.8 | Inspection | H | All known services have been located, reference back to plans to ensure everything has been located | Prior to excavation | Inspection | Sign This ITP | Supervisor/Foreman |  | 7 - Powernet and Chorus locates completed | D1.8 | Inspection / Test Point - Inspection | ACTION - H | Conformance Criteria (Whats Required) - All known services have been located, reference back to plans to ensure everything has been located | Frequency - Prior to excavation | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - | Inspection / Test Method - Review
8 | Material inspection | D2, D2.4.1 | Material Inspection | W | Complete inspection of materials as they arrive to site | Upon pipe delivery | Inspection | Sign This ITP | Supervisor/Foreman |  | 8 - Material inspection | D2, D2.4.1 | Inspection / Test Point - Material Inspection | ACTION - W | Conformance Criteria (Whats Required) - Complete inspection of materials as they arrive to site | Frequency - Upon pipe delivery | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - | Verification Records - Sign This ITP
9 | Sewerage continuity | C1.13, D2.7.5 | Monitoring | W | Ensure there is continuity in sewerage network during construction works | During construction | Inspection | Sign This ITP | Supervisor/Foreman |  | 9 - Sewerage continuity | C1.13, D2.7.5 | Inspection / Test Point - Monitoring | ACTION - W | Conformance Criteria (Whats Required) - Ensure there is continuity in sewerage network during construction works | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - | Signatory - Divisional Manager
10 | Existing alignment markout | D2.7.1, C1.14 | Inspection/Test Point | H | Markout existing aligment and trench edges onsite, to be confirmed by the Engineer's Rep | Prior to commencement | Inspection | Sign This ITP | Supervisor/Foreman |  | 10 - Existing alignment markout | D2.7.1, C1.14 | Inspection / Test Point - Inspection/Test Point | ACTION - H | Conformance Criteria (Whats Required) - Markout existing aligment and trench edges onsite, to be confirmed by the Engineer's Rep | Frequency - Prior to commencement | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - | Comments -
11 | Inspect subgrade | D13.4.3, D13.4.4 | Inspection/Scala | M | Inspect subgrade as expose, complete scala if required. Contact manager for further instruction if subgrade is deemed unsuitable | During construction | Inspection/Scala | Sign This ITP | Supervisor/Foreman |  | 11 - Inspect subgrade | D13.4.3, D13.4.4 | Inspection / Test Point - Inspection/Scala | ACTION - M | Conformance Criteria (Whats Required) - Inspect subgrade as expose, complete scala if required. Contact manager for further instruction if subgrade is deemed unsuitable | Frequency - During construction | Inspection / Test Method - Inspection/Scala | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - | 2 - Materials testing to be provided to Engineer for acceptance
12 | Pipe laying | D2, D2.7, D2.11.2 | Pipe laying | M | Pipe to be laid as per specification, contract document and plans | During construction | Spot checks | Sign This ITP | Supervisor/Foreman |  | 12 - Pipe laying | D2, D2.7, D2.11.2 | Inspection / Test Point - Pipe laying | ACTION - M | Conformance Criteria (Whats Required) - Pipe to be laid as per specification, contract document and plans | Frequency - During construction | Inspection / Test Method - Spot checks | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - | SR10.103
13 | Saddles onto main, for laterals | D4 | Sign off | W | Install as per construction plans | During construction | Photos | Sign This ITP | Supervisor/Foreman |  | 13 - Saddles onto main, for laterals | D4 | Inspection / Test Point - Sign off | ACTION - W | Conformance Criteria (Whats Required) - Install as per construction plans | Frequency - During construction | Inspection / Test Method - Photos | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - | Inspection / Test Point - Aggregate Acceptance
14 | Compaction of bedding | D1.29, D2.7.7 | Bedding | M | Compacted layers not exceeding 200mm or 1/3 the pipe OD (whichever is lesser). | During construction | Monitor | Sign This ITP | Supervisor/Foreman |  | 14 - Compaction of bedding | D1.29, D2.7.7 | Inspection / Test Point - Bedding | ACTION - M | Conformance Criteria (Whats Required) - Compacted layers not exceeding 200mm or 1/3 the pipe OD (whichever is lesser). | Frequency - During construction | Inspection / Test Method - Monitor | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - | ACTION - W
15 | Concrete pours | D1.24 | Sign off | W | Concrete pours to be inspected by Engineer's Rep prior to backfilling | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Photos/concrete dockets | 15 - Concrete pours | D1.24 | Inspection / Test Point - Sign off | ACTION - W | Conformance Criteria (Whats Required) - Concrete pours to be inspected by Engineer's Rep prior to backfilling | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - Photos/concrete dockets | Conformance Criteria (Whats Required) - Laboratory test certificates: MDD and Grading Results
16 | DN1050 Manhole F25382 | D18 | Inspection | W | Complete manhole installation checklist | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist | 16 - DN1050 Manhole F25382 | D18 | Inspection / Test Point - Inspection | ACTION - W | Conformance Criteria (Whats Required) - Complete manhole installation checklist | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - Complete SR manhole checklist | Frequency - Prior to commencement
17 | DN1050 Manhole F25381 | D18 | Inspection | W | Complete manhole installation checklist | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist | 17 - DN1050 Manhole F25381 | D18 | Inspection / Test Point - Inspection | ACTION - W | Conformance Criteria (Whats Required) - Complete manhole installation checklist | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - Complete SR manhole checklist | Inspection / Test Method - Lab report
18 | DN1050 Manhole F25380 | D18 | Inspection | W | Complete manhole installation checklist | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist | 18 - DN1050 Manhole F25380 | D18 | Inspection / Test Point - Inspection | ACTION - W | Conformance Criteria (Whats Required) - Complete manhole installation checklist | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - Complete SR manhole checklist | Verification Records - Sign This ITP
19 | DN1050 Manhole F25379 | D18 | Inspection | W | Complete manhole installation checklist | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist | 19 - DN1050 Manhole F25379 | D18 | Inspection / Test Point - Inspection | ACTION - W | Conformance Criteria (Whats Required) - Complete manhole installation checklist | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - Complete SR manhole checklist | Signatory - Contractor's Rep
20 | DN1050 Manhole F25378 | D18 | Inspection | W | Complete manhole installation checklist | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist | 20 - DN1050 Manhole F25378 | D18 | Inspection / Test Point - Inspection | ACTION - W | Conformance Criteria (Whats Required) - Complete manhole installation checklist | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - Complete SR manhole checklist | Comments -
21 | DN1050 Manhole F25377 | D18 | Inspection | W | Complete manhole installation checklist | During construction | Inspection | Sign This ITP | Supervisor/Foreman | Complete SR manhole checklist | 21 - DN1050 Manhole F25377 | D18 | Inspection / Test Point - Inspection | ACTION - W | Conformance Criteria (Whats Required) - Complete manhole installation checklist | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - Complete SR manhole checklist | 3 - Ensure Approved Plans are on site. Safety/Environmental/Quality/TMP/Permits/Site Plans
22 | Encountered Services Sheet | Contract document Appendix X, D2.7.4.3 | Record | H | Record service on ICC encountered services sheet for services found on main and laterals | During construction | Record | Sign This ITP | Supervisor/Foreman | Complete encountered service sheet for each service | 22 - Encountered Services Sheet | Contract document Appendix X, D2.7.4.3 | Inspection / Test Point - Record | ACTION - H | Conformance Criteria (Whats Required) - Record service on ICC encountered services sheet for services found on main and laterals | Frequency - During construction | Inspection / Test Method - Record | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - Complete encountered service sheet for each service | 0
23 | Drainage Connection Sheet | Contract document Appendix XI | Record | H | Record detail on ICC drainage connection sheet for each lateral installed | During construction | Record | Sign This ITP | Supervisor/Foreman | Complete drainage connection sheet for each lateral installed | 23 - Drainage Connection Sheet | Contract document Appendix XI | Inspection / Test Point - Record | ACTION - H | Conformance Criteria (Whats Required) - Record detail on ICC drainage connection sheet for each lateral installed | Frequency - During construction | Inspection / Test Method - Record | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - Complete drainage connection sheet for each lateral installed | Inspection / Test Point - Review
24 | Manhole (MH) Inspection Sheet | Contract document Appendix XV | Record | H | Record detail on ICC manhole inspection sheet for each manhole installed | During construction | Record | Sign This ITP | Supervisor/Foreman | Complete manhole installation sheet for each manhole installed | 24 - Manhole (MH) Inspection Sheet | Contract document Appendix XV | Inspection / Test Point - Record | ACTION - H | Conformance Criteria (Whats Required) - Record detail on ICC manhole inspection sheet for each manhole installed | Frequency - During construction | Inspection / Test Method - Record | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - Complete manhole installation sheet for each manhole installed | ACTION - W
25 | Plateau Testing | D2.7.7 | Test | H | Plateau test to be undertaken at start of backfill to calibrate compaction methodology | Prior to backfill | Test | Sign This ITP | Contractor's Rep |  | 25 - Plateau Testing | D2.7.7 | Inspection / Test Point - Test | ACTION - H | Conformance Criteria (Whats Required) - Plateau test to be undertaken at start of backfill to calibrate compaction methodology | Frequency - Prior to backfill | Inspection / Test Method - Test | Verification Records - Sign This ITP | Signatory - Contractor's Rep | Comments - | Conformance Criteria (Whats Required) - All plans permits produced under pre-construction available on site at all times
26 | Compaction of AP65 - Clegg Tests | Contract document Appendix XIII, D2.7.7 | Record | W | AP65 to be compacted in layers not exceeding 200mm depth. Clegg testing to be undertaken at 6m intervals. Record results on the ICC Clegg test result sheet. | During backfill | Clegg test | Sign This ITP | Supervisor/Foreman |  | 26 - Compaction of AP65 - Clegg Tests | Contract document Appendix XIII, D2.7.7 | Inspection / Test Point - Record | ACTION - W | Conformance Criteria (Whats Required) - AP65 to be compacted in layers not exceeding 200mm depth. Clegg testing to be undertaken at 6m intervals. Record results on the ICC Clegg test result sheet. | Frequency - During backfill | Inspection / Test Method - Clegg test | Verification Records - Sign This ITP | Signatory - Supervisor/Foreman | Comments - | Frequency - Prior to commencement
27 | Compaction of AP65 - Test Results to Engineer | D1.29, D2.7 | Test Point | W | NDM testing to be undertaken every 120m and achieve compaction of at least 95%. Results to be provided to Engineer at end of each stage. | During construction | NDM Test | Sign This ITP | Contractor's Rep | NDM test results | 27 - Compaction of AP65 - Test Results to Engineer | D1.29, D2.7 | Inspection / Test Point - Test Point | ACTION - W | Conformance Criteria (Whats Required) - NDM testing to be undertaken every 120m and achieve compaction of at least 95%. Results to be provided to Engineer at end of each stage. | Frequency - During construction | Inspection / Test Method - NDM Test | Verification Records - Sign This ITP | Signatory - Contractor's Rep | Comments - NDM test results | Inspection / Test Method - Review
28 | Compaction of AP40 - Test Results to Engineer | D1.29, D2.7 | Test Point | W | NDM testing to be undertaken every 20m and achieve compaction of at least 98%. Results to be provided to Engineer at end of each stage. | During construction | NDM Test | Sign This ITP | Contractor's Rep | NDM test results | 28 - Compaction of AP40 - Test Results to Engineer | D1.29, D2.7 | Inspection / Test Point - Test Point | ACTION - W | Conformance Criteria (Whats Required) - NDM testing to be undertaken every 20m and achieve compaction of at least 98%. Results to be provided to Engineer at end of each stage. | Frequency - During construction | Inspection / Test Method - NDM Test | Verification Records - Sign This ITP | Signatory - Contractor's Rep | Comments - NDM test results | Verification Records - Sign This ITP
29 | Foul sewer main pressure testing | AS/NZS2566:2 | Test Point | H | Pressure test of new main, including connections to boundary | During construction | Pressure test | Sign This ITP | Supervisor/Contractor's Rep |  | 29 - Foul sewer main pressure testing | AS/NZS2566:2 | Inspection / Test Point - Test Point | ACTION - H | Conformance Criteria (Whats Required) - Pressure test of new main, including connections to boundary | Frequency - During construction | Inspection / Test Method - Pressure test | Verification Records - Sign This ITP | Signatory - Supervisor/Contractor's Rep | Comments - | Signatory - Contractor's Rep
30 | Height check and CCTV - MH F25382 - F25381 | D2.9.3 | Sign off | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage | 30 - Height check and CCTV - MH F25382 - F25381 | D2.9.3 | Inspection / Test Point - Sign off | ACTION - H | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Contractor's Rep | Comments - CCTV footage | Comments -
31 | Height check and CCTV - MH F25381 - F25380 | D2.9.3 | Sign off | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage | 31 - Height check and CCTV - MH F25381 - F25380 | D2.9.3 | Inspection / Test Point - Sign off | ACTION - H | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Contractor's Rep | Comments - CCTV footage | 4 - Notice to Engineer Reviewed by Divisional Manager
32 | Height check and CCTV - MH F25380 - F25379 | D2.9.3 | Sign off | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage | 32 - Height check and CCTV - MH F25380 - F25379 | D2.9.3 | Inspection / Test Point - Sign off | ACTION - H | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Contractor's Rep | Comments - CCTV footage | 0
33 | Height check and CCTV - MH F25379 - F25378 | D2.9.3 | Sign off | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage | 33 - Height check and CCTV - MH F25379 - F25378 | D2.9.3 | Inspection / Test Point - Sign off | ACTION - H | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Contractor's Rep | Comments - CCTV footage | Inspection / Test Point - Review
34 | Height check and CCTV - MH F25378 - F25377 | D2.9.3 | Sign off | H | Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. | During construction | Inspection | Sign This ITP | Supervisor/Contractor's Rep | CCTV footage | 34 - Height check and CCTV - MH F25378 - F25377 | D2.9.3 | Inspection / Test Point - Sign off | ACTION - H | Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt. | Frequency - During construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Supervisor/Contractor's Rep | Comments - CCTV footage | ACTION - W
35 | Asphalt prep | D2.8, D12 | Sign off | H | Engineer to approve area is ready for asphalt. Prep and overcuts completed and compaction results satisfactory. | Prior to asphalt | Inspection | Sign This ITP | Engineer/Engineer's Rep |  | 35 - Asphalt prep | D2.8, D12 | Inspection / Test Point - Sign off | ACTION - H | Conformance Criteria (Whats Required) - Engineer to approve area is ready for asphalt. Prep and overcuts completed and compaction results satisfactory. | Frequency - Prior to asphalt | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Engineer/Engineer's Rep | Comments - | Conformance Criteria (Whats Required) - All NTE's to be reviewed
36 | Defect walkovers |  | Inspection | H | Contract management team to walk over site and inspect for any defects. List to be made by Engineer and provided to SR for rectification. | Post construction | Inspection | Sign This ITP | Contractor's Rep |  | 36 - Defect walkovers | 0 | Inspection / Test Point - Inspection | ACTION - H | Conformance Criteria (Whats Required) - Contract management team to walk over site and inspect for any defects. List to be made by Engineer and provided to SR for rectification. | Frequency - Post construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Contractor's Rep | Comments - | Frequency - Prior to submission to Engineer
37 | Supply of QA documentation | D17 | Sign off | W | Remaining QA documentation to be uploaded into Sharepoint | Post construction | Inspection | Sign This ITP | Contractor's Rep |  | 37 - Supply of QA documentation | D17 | Inspection / Test Point - Sign off | ACTION - W | Conformance Criteria (Whats Required) - Remaining QA documentation to be uploaded into Sharepoint | Frequency - Post construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Contractor's Rep | Comments - | Inspection / Test Method - Review
38 | Supply of Asbuilts | D17 | Sign off | W | Asbuilt data, DWG format drawings and red pen mark- ups provided to Engineer | Post construction | Inspection | Sign This ITP | Contractor's Rep |  | 38 - Supply of Asbuilts | D17 | Inspection / Test Point - Sign off | ACTION - W | Conformance Criteria (Whats Required) - Asbuilt data, DWG format drawings and red pen mark- ups provided to Engineer | Frequency - Post construction | Inspection / Test Method - Inspection | Verification Records - Sign This ITP | Signatory - Contractor's Rep | Comments - | Verification Records - Sign This ITP
Signatory - Contractor's Rep
Comments -
5 - Variations Reviewed by Divisional Manager
0
Inspection / Test Point - Review
ACTION - W
Conformance Criteria (Whats Required) - All Variations to be reviewed
Frequency - Prior to submission to Engineer
Inspection / Test Method - Review
Verification Records - Sign This ITP
Signatory - Contractor's Rep
Comments -
6 - Site Pre-Condition Inspection
D1.5, D1.32.4
Inspection / Test Point - Review
ACTION - W
Conformance Criteria (Whats Required) - Record existing condition of site via walk-over/drive-over
Frequency - Prior to excavation
Inspection / Test Method - Video
Verification Records - Sign This ITP
Signatory - Contractor's Rep
Comments -
7 - Powernet and Chorus locates completed
D1.8
Inspection / Test Point - Inspection
ACTION - H
Conformance Criteria (Whats Required) - All known services have been located, reference back to plans to ensure everything has been located
Frequency - Prior to excavation
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments -
8 - Material inspection
D2, D2.4.1
Inspection / Test Point - Material Inspection
ACTION - W
Conformance Criteria (Whats Required) - Complete inspection of materials as they arrive to site
Frequency - Upon pipe delivery
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments -
9 - Sewerage continuity
C1.13, D2.7.5
Inspection / Test Point - Monitoring
ACTION - W
Conformance Criteria (Whats Required) - Ensure there is continuity in sewerage network during construction works
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments -
10 - Existing alignment markout
D2.7.1, C1.14
Inspection / Test Point - Inspection/Test Point
ACTION - H
Conformance Criteria (Whats Required) - Markout existing aligment and trench edges onsite, to be confirmed by the Engineer's Rep
Frequency - Prior to commencement
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments -
11 - Inspect subgrade
D13.4.3, D13.4.4
Inspection / Test Point - Inspection/Scala
ACTION - M
Conformance Criteria (Whats Required) - Inspect subgrade as expose, complete scala if required. Contact manager for further instruction if subgrade is deemed unsuitable
Frequency - During construction
Inspection / Test Method - Inspection/Scala
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments -
12 - Pipe laying
D2, D2.7, D2.11.2
Inspection / Test Point - Pipe laying
ACTION - M
Conformance Criteria (Whats Required) - Pipe to be laid as per specification, contract document and plans
Frequency - During construction
Inspection / Test Method - Spot checks
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments -
13 - Saddles onto main, for laterals
D4
Inspection / Test Point - Sign off
ACTION - W
Conformance Criteria (Whats Required) - Install as per construction plans
Frequency - During construction
Inspection / Test Method - Photos
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments -
14 - Compaction of bedding
D1.29, D2.7.7
Inspection / Test Point - Bedding
ACTION - M
Conformance Criteria (Whats Required) - Compacted layers not exceeding 200mm or 1/3 the pipe OD (whichever is lesser).
Frequency - During construction
Inspection / Test Method - Monitor
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments -
15 - Concrete pours
D1.24
Inspection / Test Point - Sign off
ACTION - W
Conformance Criteria (Whats Required) - Concrete pours to be inspected by Engineer's Rep prior to backfilling
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments - Photos/concrete dockets
16 - DN1050 Manhole F25382
D18
Inspection / Test Point - Inspection
ACTION - W
Conformance Criteria (Whats Required) - Complete manhole installation checklist
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments - Complete SR manhole checklist
17 - DN1050 Manhole F25381
D18
Inspection / Test Point - Inspection
ACTION - W
Conformance Criteria (Whats Required) - Complete manhole installation checklist
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments - Complete SR manhole checklist
18 - DN1050 Manhole F25380
D18
Inspection / Test Point - Inspection
ACTION - W
Conformance Criteria (Whats Required) - Complete manhole installation checklist
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments - Complete SR manhole checklist
19 - DN1050 Manhole F25379
D18
Inspection / Test Point - Inspection
ACTION - W
Conformance Criteria (Whats Required) - Complete manhole installation checklist
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments - Complete SR manhole checklist
20 - DN1050 Manhole F25378
D18
Inspection / Test Point - Inspection
ACTION - W
Conformance Criteria (Whats Required) - Complete manhole installation checklist
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments - Complete SR manhole checklist
21 - DN1050 Manhole F25377
D18
Inspection / Test Point - Inspection
ACTION - W
Conformance Criteria (Whats Required) - Complete manhole installation checklist
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments - Complete SR manhole checklist
22 - Encountered Services Sheet
Contract document Appendix X, D2.7.4.3
Inspection / Test Point - Record
ACTION - H
Conformance Criteria (Whats Required) - Record service on ICC encountered services sheet for services found on main and laterals
Frequency - During construction
Inspection / Test Method - Record
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments - Complete encountered service sheet for each service
23 - Drainage Connection Sheet
Contract document Appendix XI
Inspection / Test Point - Record
ACTION - H
Conformance Criteria (Whats Required) - Record detail on ICC drainage connection sheet for each lateral installed
Frequency - During construction
Inspection / Test Method - Record
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments - Complete drainage connection sheet for each lateral installed
24 - Manhole (MH) Inspection Sheet
Contract document Appendix XV
Inspection / Test Point - Record
ACTION - H
Conformance Criteria (Whats Required) - Record detail on ICC manhole inspection sheet for each manhole installed
Frequency - During construction
Inspection / Test Method - Record
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments - Complete manhole installation sheet for each manhole installed
25 - Plateau Testing
D2.7.7
Inspection / Test Point - Test
ACTION - H
Conformance Criteria (Whats Required) - Plateau test to be undertaken at start of backfill to calibrate compaction methodology
Frequency - Prior to backfill
Inspection / Test Method - Test
Verification Records - Sign This ITP
Signatory - Contractor's Rep
Comments -
26 - Compaction of AP65 - Clegg Tests
Contract document Appendix XIII, D2.7.7
Inspection / Test Point - Record
ACTION - W
Conformance Criteria (Whats Required) - AP65 to be compacted in layers not exceeding 200mm depth. Clegg testing to be undertaken at 6m intervals. Record results on the ICC Clegg test result sheet.
Frequency - During backfill
Inspection / Test Method - Clegg test
Verification Records - Sign This ITP
Signatory - Supervisor/Foreman
Comments -
27 - Compaction of AP65 - Test Results to Engineer
D1.29, D2.7
Inspection / Test Point - Test Point
ACTION - W
Conformance Criteria (Whats Required) - NDM testing to be undertaken every 120m and achieve compaction of at least 95%. Results to be provided to Engineer at end of each stage.
Frequency - During construction
Inspection / Test Method - NDM Test
Verification Records - Sign This ITP
Signatory - Contractor's Rep
Comments - NDM test results
28 - Compaction of AP40 - Test Results to Engineer
D1.29, D2.7
Inspection / Test Point - Test Point
ACTION - W
Conformance Criteria (Whats Required) - NDM testing to be undertaken every 20m and achieve compaction of at least 98%. Results to be provided to Engineer at end of each stage.
Frequency - During construction
Inspection / Test Method - NDM Test
Verification Records - Sign This ITP
Signatory - Contractor's Rep
Comments - NDM test results
29 - Foul sewer main pressure testing
AS/NZS2566:2
Inspection / Test Point - Test Point
ACTION - H
Conformance Criteria (Whats Required) - Pressure test of new main, including connections to boundary
Frequency - During construction
Inspection / Test Method - Pressure test
Verification Records - Sign This ITP
Signatory - Supervisor/Contractor's Rep
Comments -
30 - Height check and CCTV - MH F25382 - F25381
D2.9.3
Inspection / Test Point - Sign off
ACTION - H
Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Contractor's Rep
Comments - CCTV footage
31 - Height check and CCTV - MH F25381 - F25380
D2.9.3
Inspection / Test Point - Sign off
ACTION - H
Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Contractor's Rep
Comments - CCTV footage
32 - Height check and CCTV - MH F25380 - F25379
D2.9.3
Inspection / Test Point - Sign off
ACTION - H
Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Contractor's Rep
Comments - CCTV footage
33 - Height check and CCTV - MH F25379 - F25378
D2.9.3
Inspection / Test Point - Sign off
ACTION - H
Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Contractor's Rep
Comments - CCTV footage
34 - Height check and CCTV - MH F25378 - F25377
D2.9.3
Inspection / Test Point - Sign off
ACTION - H
Conformance Criteria (Whats Required) - Check heights during construction. CCTV new line to ensure quality of installation prior to asphalt.
Frequency - During construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Supervisor/Contractor's Rep
Comments - CCTV footage
35 - Asphalt prep
D2.8, D12
Inspection / Test Point - Sign off
ACTION - H
Conformance Criteria (Whats Required) - Engineer to approve area is ready for asphalt. Prep and overcuts completed and compaction results satisfactory.
Frequency - Prior to asphalt
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Engineer/Engineer's Rep
Comments -
36 - Defect walkovers
0
Inspection / Test Point - Inspection
ACTION - H
Conformance Criteria (Whats Required) - Contract management team to walk over site and inspect for any defects. List to be made by Engineer and provided to SR for rectification.
Frequency - Post construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Contractor's Rep
Comments -
37 - Supply of QA documentation
D17
Inspection / Test Point - Sign off
ACTION - W
Conformance Criteria (Whats Required) - Remaining QA documentation to be uploaded into Sharepoint
Frequency - Post construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Contractor's Rep
Comments -
38 - Supply of Asbuilts
D17
Inspection / Test Point - Sign off
ACTION - W
Conformance Criteria (Whats Required) - Asbuilt data, DWG format drawings and red pen mark- ups provided to Engineer
Frequency - Post construction
Inspection / Test Method - Inspection
Verification Records - Sign This ITP
Signatory - Contractor's Rep
Comments -