## matrix
Matrix Name | Dimension | Name | Type / Data Field | Tag 1 | Tag 2
Cut Floor - Lot Register
| Scope |  |  | Site QA | Cut Floor
Rows
|  | McGregor Road North | dynamic | McGregor Rd - North | Cut Floor | Site QA
|  | McGregor Road South | dynamic | McGregor Rd - South | Cut Floor | Site QA
|  | HKWRR North | dynamic | HKWRR North | Cut Floor | Site QA
|  | HKWRR South | dynamic | HKWRR South | Cut Floor | Site QA
Columns
|  | Lot Map | Lot map | 1.1.1 - Lot Map | 1.0 Pre-start activities
|  | CHAINAGE FROM | CHAINAGE FROM | 1.1 - Commencement of Work | 1.0 Pre-start activities
|  | CHAINAGE TO | CHAINAGE TO | 1.1 - Commencement of Work | 1.0 Pre-start activities
|  | Surveyor Report Reference | Surveyor report reference | 1.3.1 - Surveyor Report Reference | 1.0 Pre-start activities
|  | Signed Hold Points |  | AUTHORITY HOLDPOINT
|  | Incoming Material Docket | Incoming material docket | 2.0.1 - Incoming Material Docket | 2.0 Construction
Compaction Test Result
|  | Proof Roll | Proof roll if applicable - comment reasoning if N/A | 3.8.1 - Proof roll if applicable | 3.0 Treatment of Cut / Rock Subgrade
|  | CBR Test Result | NATA Test Report: CBR and Swell | 3.3 - Testing In-situ Material in Cuts | 3.0 Treatment of Cut / Rock Subgrade
|  | NCR | NCR raised? | Lot Conformance | 4.0 Work Lot Close Out
|  | Lot Status | Lot Status | Lot Conformance | 4.0 Work Lot Close Out
|  | Lot Opened On | Lot opened date: | Lot Conformance | 4.0 Work Lot Close Out
|  | Lot Opened By | Lot opened by: | Lot Conformance | 4.0 Work Lot Close Out
|  | Comments | Comments | Lot Conformance | 4.0 Work Lot Close Out